GARISSA UNIVERSITY

BY DR ROSALIA  MUMO

Course Code: CIM 8123

Course Title: MONITORING AND EVALUATION

Credit Hrs:

Pre-requisite: None>Masharti ya awali: Hakuna

Course Purpose>Madhumuni ya Kozi

The aim of the unit is to expose learners to best practices in monitoring and evaluation of educational institutions, programmes and systems.

Learners will acquire knowledge and skills in monitoring and evaluation to facilitate effective performance.

Lengo la somo hili ni kuwawezesha wanafunzi kufahamu mbinu bora za ufuatiliaji na tathmini (monitoring and evaluation) katika taasisi, programu na mifumo ya elimu.
Wanafunzi watapata maarifa na stadi za kufanya ufuatiliaji na tathmini ili kuwezesha utendaji bora.

Okogania kwo’gosoma oko nogokora abanafunzi komanya chinjera chingiya chio’gofuatlia na gopima naki chinsemo chia’masomo, chiprogramu na chisysytemu chigokora egasi.

Abanafunzi mbanyore obosemi na obomanyi bwo’gofuatlia na gopima elinde egasi ekoreke buya.

Expected Learning Outcomes>Matokeo Tarajiwa ya Kujifunza.

By the end of the unit, learners should be able to:>Mwisho wa somo hili, wanafunzi wanapaswa kuwa na uwezo wa:

- Explain the foundations of monitoring and evaluation.

- Eleza misingi ya ufuatiliaji na tathmini.

- Examine the theoretical basis of monitoring and evaluation.

- Chunguza msingi wa nadharia wa ufuatiliaji na tathmini.

- Differentiate between monitoring and evaluation.

- Tofauti kati ya ufuatiliaji na tathmini.

- Describe the approaches of monitoring and evaluation suitable for education.

- Eleza mbinu za ufuatiliaji na tathmini zinazofaa kwa elimu.

- Analyze monitoring and evaluation methods showing their relevance to education.

- Chambua mbinu za ufuatiliaji na tathmini ukionyesha umuhimu wake katika elimu.

- Discuss monitoring and evaluation requirements and practices

- Jadili mahitaji na mbinu za ufuatiliaji na tathmini

- Carry out effective and efficient monitoring and evaluation of educational programmes and projects using the tools learnt.

- Fanya ufuatiliaji na tathmini wa kina na wenye ufanisi wa programu na miradi ya kielimu kwa kutumia zana ulizojifunza.

- Successfully monitor and evaluate curricula to improve instruction.

- Kufuatilia na kutathmini mtaala kwa mafanikio ili kuboresha ufundishaji.

- Acquaint themselves with monitoring and evaluation tools used by the UNESCO and other Development agencies.

- Kujifunza na kufahamiana na zana za ufuatiliaji na tathmini zinazotumika na UNESCO na mashirika mengine ya maendeleo.

Course Content> Yaliyomo kwenye Kozi

- The Foundations of Education Monitoring and Evaluation.

Msingi wa Ufuatiliaji na Tathmini ya Elimu

- Purpose of Monitoring and Evaluation.

Madhumuni ya Ufuatiliaji na Tathmini

- Theoretical underpinnings of Monitoring and Evaluation.

Misingi ya Nadharia ya Ufuatiliaji na Tathmini

- Basic concepts of Monitoring and Evaluation:

Madhara ya Msingi ya Ufuatiliaji na Tathmini:

- The concept of monitoring, the concept of evaluation.

Dhana ya ufuatiliaji, dhana ya tathmini

- Principles of Monitoring and Evaluation,

Kanuni za Ufuatiliaji na Tathmini

- Approaches to Monitoring and Evaluation.

Mbinu za Ufuatiliaji na Tathmini

- Methodologies of Monitoring and Evaluation.

Falsafa na Mbinu za Ufuatiliaji na Tathmini

- Performance Based Monitoring and Evaluation in Practice.

Ufuatiliaji na Tathmini unaotegemea Utendaji (Performance Based) katika Vitendo

- Monitoring and Evaluation tools.

Vyombo vya Ufuatiliaji na Tathmini

- Monitoring and Evaluation Requirements and processes.

Mahitaji na Taratibu za Ufuatiliaji na Tathmini

- Use of Monitoring and Evaluation results.

Matumizi ya Matokeo ya Ufuatiliaji na Tathmini

Teaching methodology >Mbinu za kufundishia

The mode of instruction will include lectures, group discussion, individual study, class presentation, tests, assignments and examinations.

Njia za kufundishia zitajumuisha mihadhara, majadiliano ya kikundi, masomo binafsi, uwasilishaji darasani, mitihani midogo, kazi za nyumbani na mitihani mikubwa.

Instructional materials

The following will be some of the instructional materials to be used: chalk board, PowerPoint presentations, resource persons, reference books and journal articles.

Vifaa vya kufundishia vitakavyotumika ni pamoja na: ubao wa mchoro, mawasilisho ya PowerPoint, watu wa rasilimali, vitabu vya rejeleo na makala za vikao vya kitaaluma.

Course Assessment>Tathmini ya Kozi

Continuous assessment> Tathmini endelevu.                                                      30%

End of semester examinations>   Mtihani wa Mwisho wa Muhula                   70%

Total> Jumla.                                                                                                      100%

Recommended Reference Materials> Vyanzo vya Marejeleo Vilivyopendekezwa

- http//www. World Bank org/ieg/ecd (2009), OECD and world Monitoring and Evaluation some tools methods and approaches (2004).

- Body 2.K. and day C. List – Ten steps Cr a results based management and evaluation: a handbook for development practitioners (2004).

- IFAT A guide to monitoring and Evaluation managing for in rural management.

- Waguer et-al – World Bank Monitoring and Evaluation of ICT in educational project a hand book for developing countries (2005)

- Philip – Bartle ( 2007) Monitoring and Evaluation: how well objectives are being reached

Guidelines on quality provision to cross border higher education (2000)>Mwongozo wa utoaji wa elimu ya juu ya ubora kwa mipaka ya nchi (2000)

MONITORING AND EVALUATION USES SPECIFIC TOOLS/TECHNIQUES.

Ufuatiliaji na tathmini hutumia zana/mbinu maalum.

TECHNIQUES/TOOLS OF ASSESSMENT >MBINU/VIFAA VYA TATHMINI>qcrio

1. CHECKLIST

Definition

A checklist is a structured tool that lists specific items, activities, behaviors, or conditions to be checked, verified, or observed during monitoring or evaluation.

Merits (8)

Easy to use and understand.

Saves time during data collection.

Ensures consistency across different observers.

Helps avoid forgetting important items.

Useful for routine monitoring.

Supports quick comparison of performance over time.

Can be used by staff with minimal training.

Produces standardized data.

Demerits (8)

Provides limited depth of information.

May oversimplify complex issues.

Restricted to predetermined items only.

Not suitable for capturing unexpected findings.

Rigid format may reduce flexibility.

Observer bias can still occur.

Does not explain reasons behind observations.

Poorly designed checklists lead to incomplete data.

2. QUESTIONNAIRE

Definition

A questionnaire is a written set of structured or semi-structured questions used to gather information from respondents in a standardized way.

Merits (8)

Can reach many respondents quickly.

Cost-effective, especially for large samples.

Reduces interviewer bias when self-administered.

Produces comparable and quantifiable data.

Ensures anonymity, increasing honesty.

Easy to analyse statistically.

Can be distributed online or in print.

Allows respondents to answer at their own pace.

Demerits (8)

Low response rates if not well followed-up.

Misinterpretation of questions by respondents.

Limited ability to probe deeper.

Not suitable for illiterate participants.

Respondents may skip difficult questions.

Social desirability bias may affect answers.

Time-consuming to design a good questionnaire.

Cannot observe non-verbal cues.

3. OBSERVATION GUIDE

Definition

An observation guide is a structured tool outlining specific behaviors, actions, events, or conditions to be observed systematically in a natural setting.

Merits (8)

Captures real-time, natural behaviour.

Useful for participants who cannot express themselves well.

Provides rich, detailed data.

Helps verify accuracy of reported information.

Minimizes recall bias.

Useful for monitoring processes or activities.

Allows understanding of context and environment.

Can capture non-verbal cues.

Demerits (8)

Observer presence may influence behaviour (Hawthorne effect).

Time-consuming and labor-intensive.

Requires skilled, trained observers.

Observer bias may distort findings.

Difficult to observe large samples.

Some behaviors occur unpredictably and may be missed.

Not suitable for sensitive or hidden activities.

Analysis of observation data may be complex.

4. INTERVIEW GUIDE

Definition

An interview guide is a structured or semi-structured list of questions and prompts used by interviewers to collect detailed and in-depth information from respondents.

Merits (8)

Allows probing for deeper insights.

Offers flexibility in question phrasing.

Enables clarification of unclear responses.

Captures detailed, rich qualitative data.

Allows observation of non-verbal communication.

Builds rapport, increasing honest responses.

Suitable for illiterate respondents.

Adaptable to different contexts and topics.

Demerits (8)

Time-consuming to conduct.

Requires well-trained interviewers.

Interviewer bias may influence responses.

Difficult to reach large samples.

Responses may be influenced by social desirability.

Expensive due to travel and personnel costs.

Requires transcription, which is time-consuming.

Inconsistent questioning reduces comparability.

5. RECORDS (Document Review/Record Analysis)

Definition

Records are existing written or digital documents—such as attendance registers, reports, financial statements, test scores, and logs—used to obtain secondary data during M&E.

Merits (8)

Data already exists and is easy to access.

Cost-effective as it avoids new data collection.

Useful for historical comparisons.

Provides objective and authentic data.

Good for verifying primary data.

Less time-consuming than fieldwork.

Helps track trends over long periods.

Useful for routine monitoring (e.g., attendance records).

Demerits (8)

Records may be incomplete or inaccurate.

Missing data cannot be recovered.

Variability in record-keeping affects reliability.

Outdated documents may mislead evaluation.

Access may be restricted due to confidentiality.

Data may not match the evaluator’s information needs.

Poor storage leads to loss or damage.

Sometimes difficult to verify authenticity.

- Questionnaires

- Dodoso

- Observation guide

- Mwongozo wa Uchunguzi

Interview guide

Mwongozo wa mahojiano

- Focus group discussion guide- Checklist

- Mwongozo wa Majadiliano ya Kikundi cha Kuzingatia – Orodhesha Vitu (Checklist)

- Records >Rekodi au Hati (kulingana na muktadha).

- What are they?> Ni nini?

- What kind of data can be collected using the instrument?

- Ni aina gani ya data inaweza kukusanywa kwa kutumia chombo hicho?

- How do we administer the instrument?

- Tunaendeshaje kutumia kifaa hicho?

- What are the merits and demerits of using this method?

- Je, faida na hasara za kutumia njia hii ni zipi?

Definitions: What is monitoring?>Maelezo: Ufuatiliaji ni nini?

Monitoring refers to the routine process of assessing progress of particular projects through data collection.

Ufuatiliaji (Monitoring) unarejelea mchakato wa kawaida wa kutathmini maendeleo ya miradi maalum kupitia ukusanyaji wa data.

Evaluation is the process of finding value or looking for value in a project, document, an activity (intention of making decision).

Tathmini ni mchakato wa kubaini thamani au kutafuta thamani katika mradi, hati, au shughuli (kwa nia ya kufanya uamuzi).

Monitoring is associated with the collection or gathering of information concerning an on-going project.

Ufuatiliaji unahusiana na ukusanyaji au kukusanya taarifa zinazohusu mradi unaoendelea.

What is evaluation?>Tathmini ni nini?

Tathmini ni mchakato wa kukusanya na kuchambua taarifa ili kubaini ubora, ufanisi, na matokeo ya shughuli, programu, au mfumo fulani.

The term evaluation has a variety of meanings basically anything in the school can be evaluated in terms of its contribution to the students overall learning and its cost. Eg the school personnel can evaluate the basic worth of a programmes objectives, content, activities, plans, materials or methods of delivering, student’s performance, teacher’s skills, attitudes and behaviors, student skills and attitudes.

Neno tathmini lina maana mbalimbali; kwa msingi wowote, chochote shuleni kinaweza kutathminiwa kwa kuzingatia mchango wake katika ujifunzaji wa jumla wa mwanafunzi na gharama yake. Kwa mfano, wafanyakazi wa shule wanaweza kutathmini thamani msingi ya malengo ya programu, maudhui, shughuli, mipango, vifaa au mbinu za kufundisha, utendaji wa wanafunzi, stadi za walimu, mitazamo na tabia, pamoja na stadi na mitazamo ya wanafunzi.

Evaluation can also be done at various levels eg. Classroom level school, zonal, division, sub- county, county and national level.

Tathmini pia inaweza kufanywa katika ngazi mbalimbali, mfano: ngazi ya darasa, shule, mkoa/mdara wa kijiwa, kaunti, na ngazi ya kitaifa.

DEFINITION OF EVALUATION>UFASIRI WA TATHMINI

- Evaluation is a process or a cluster of processes that people perform in order to gather data that will enable them to decide whether to accept change or eliminate something in the curriculum in general or an aspect in the curriculum.

- The concern is to determine relative value (compare)

- Tathmini ni mchakato au kundi la michakato ambayo watu hufanya ili kukusanya data itakayowawezesha kuamua kama watakubali mabadiliko au kuondoa jambo fulani katika mtaala kwa ujumla au kipengele fulani cha mtaala.

- Lengo ni kubaini thamani ya ulinganifu (kulinganisha)

- Worthing and sanders

- “Curriculum evaluation is the determination of the worthy/value of a thing” This includes obtaining information for use in judging the worth of a programme, product, procedures, objective or the potential utility of alternative approaches designed to attain specified objectives.

- "Tathmini ya mtaala ni utambuzi wa thamani ya jambo." Hii inajumuisha kupata taarifa kwa ajili ya kutumika katika kuhakiki thamani ya programu, bidhaa, taratibu, lengo au ufanisi unaowezekana wa mbinu mbadala zilizoundwa kufikia malengo maalum.

- Bruce Talkman- Curriculum evaluation> Tathmini ya mtaala

- Is the means for determining whether programme is meeting its goals.

- Ni njia ya kubaini kama programu inafanikisha malengo yake.

- Daniel stuffle beam – Defines C.E as the process of delineanling, obtaining and providing useful information for judging decision alternatives (accept, eliminate or change)

- Hufafanua C.E kama mchakato wa kufafanua, kupata na kutoa taarifa muhimu kwa ajili ya kutathmini mbadala za maamuzi (kubali, tolea au badilisha).

- In evaluation we make a decision always.

- Katika tathmini, kila wakati tunafanya uamuzi.

- All the scholars mentioned above view evaluation as a process of identifying and gathering information that will help decision makers choose various courses of action for creating and delivering curricular. Decision making is central in evaluation.

- Wanasayansi wote waliotajwa hapo juu wanaona tathmini kama mchakato wa kutambua na kukusanya taarifa ambazo zitasaidia watendaji wa maamuzi kuchagua njia mbalimbali za hatua katika kuunda na kutoa mtaala. Kufanya maamuzi kunachukua nafasi ya msingi katika tathmini.

Who can evaluate?> Nani anaweza kufanya tathmini?

The teachers, specialists, managers, learners (internal evaluators). Those within the school.

-External evaluators – Specialists, experts, teachers, advisory centres (Titles) QASOS, no experts, participants at community level.

Walimu, wataalamu, wasimamizi, na wanafunzi (watafiti wa ndani). Hawa wote wako ndani ya shule.

Watafiti wa nje – Wataalamu, mtaalamu maalumu, walimu, vituo vya ushauri (vyeo) QASOS, hakuna wataalamu, washiriki kwenye ngazi ya jamii.

External evaluators>Waangalizi wa nje

This is a person who is able to take a fresh look at a programme because he/she is not involved personally and has nothing to lose or gain from the evaluation.

Huyu ni mtu ambaye anaweza kuangalia programu kwa mtazamo mpya kwa sababu hajashiriki moja kwa moja na hana cha kupoteza au kupata kutokana na tathmini hiyo.

Internal Evaluators> Wakaguzi wa Ndani

This is the person ‘inside’ the programme or who knows(SWOT) the objectives, problems, strengths and weaknesses of the programme eg programme manager, co-ordinator, teachers, KIE.

Huyu ni mtu aliye ‘ndani’ ya programu au anayejua (SWOT) malengo, changamoto, nguvu na udhaifu wa programu, mfano meneja wa programu, ko-odineti, walimu, KIE.

COMPARE THE INTERNAL AND EXTERNAL EVALUATION> LINGANISHA TATHMINI YA NDANI NA YA NJE

INTERNAL> Wakaguzi wa Ndani

- Biased in the evaluation(subjective) something to loose.

- Ni tathmini yenye upendeleo (ya kibinafsi) – kitu cha kupoteza.

- Familiar with the programme and understands it well better placed to evaluate.

- Anafahamu programu na anaielewa vizuri, hivyo ameweka nafasi nzuri ya kufanya tathmini.

- May not necessary be a specialist in evaluation.

- Haijalishi awe mtaalamu wa tathmini.

- He/she is a stakeholder.

- Yeye ni mhusika/chini ya hisa.

- (Kwa muktadha wa elimu au miradi, mara nyingi stakeholder hutafsiriwa kama mhusika au mshiriki.)

- May overlook some certain issues.

- Inaweza kupuuza baadhi ya masuala fulani.

- May be objective in the remarks eg. TEAM

- Inaweza kuwa ya wazi katika maoni, kwa mfano.

- Measurement ( use of numerical set criteria standards)

- Upimaji (matumizi ya viwango vya kima nambari)

- Testing – test>Kujaribu – jaribio

- Assessing – marking>Kadiria – kutoa alama

- Evaluating – Comments eg v.good value judgment.

- Kutathmini – Maoni, kwa mfano: hukumu nzuri sana ya thamani.

May not cause anxiety or disruption final recommendations made. May look less threatening.

Haiwezi kusababisha wasiwasi au kuvuruga mapendekezo ya mwisho yaliyotolewa. Inaweza kuonekana isiyo ya hatari.

EXTERNAL

- Objective-- nothing to lose.

- Outsiders who may not necessary understand the programme very well.

- Must be a specialist.

- Do it as an assignment.

- May look at it with a critical eye.

- May work under pressure eg if politically appointed

- Cause anxiety and their recommendations look more threatening.

FACTORS /POINTS TO CONSIDER WHEN EVALUATING

Time, resources,objectives,methods,

- The life span /time span of the programme eg 5, 10 yrs etc

- Resources available- budget for them eg human, financial.

- The objective of the evaluation.

- The monitoring methods that are already in place.  If we have effective monitoring system in a programme may not need a mid-term.

- Are external evaluators to be involved?

- Peoples time- when are they available?

- The climate – The weather and season eg when you want to carry out a research.

- Time of the programme staff, ministries and outside agencies.

- It is usually easier to show failure than success of a programme especially where funding is stake. The reason why it is not possible for evaluation to show clearly success or failure at one time can be regarded as partly successful.

- Success or failure mean different things to different people e.g. water projects can make environment pollution.

- Evaluation deals with things that can be counted and or measured e.g. people products, services, amount of materials, resources available, financial costs, extent of areas cultivated etc. deals with numbers , amounts or quantities- these are called quantitative aspects of evaluation.

- It also deals with qualitative e.g. services beneficiaries and service providers.

- The qualitative aspects of evaluation consists of peoples behavior, their attitudes and values, abilities, peoples relationships, skills etc.

- An aspect of evaluation is important because it helps explain why a programme in a particular place proceeds in a particular way and why it has particular strengths -SWOT and weaknesses, problems and solutions expected and unexpected outcomes.

REASONS FOR EVALUATION

>for SWOT

1 For achievement i.e to confirm /assess what has been achieved.

2. To identify areas of strengths and weaknesses.

3. To improve on the monitoring.

4. To continue funding the programme.

5. For cost-benefit analysis – are the costs reasonable?

6 For replication

7. For scaling up eg from pilot to wide scale.

8 For collecting information for better re-designation, plan and magnitude.

9 For justification and accountability.

11. For knowledge - learning something.

12. To measure the progress in accordance to the set objectives.

13. Because the funding agency has asked the evaluators to do so.

14. Because the researcher want to try a new technique.

15. To mark the end of the programme.

14 For comparison within different regions.

Evaluation is like looking to see where and how fast we are going and then estimating when we are likely to meet our destinations.

- WAJENZI WA NJE (EXTERNAL)

- Lengo – hakuna la kupoteza.

- Watu wa nje ambao huenda hawana uelewa mzuri wa programu.

- Lazima awe mtaalamu.

- Kufanya kama kazi ya makazi/assignment.

- Anaweza kuangalia kwa jicho la ukali.

- Anaweza kufanya kazi chini ya shinikizo, mfano kama ameajiriwa kisiasa.

- Kusababisha wasiwasi na mapendekezo yao kuonekana hatari zaidi.

- VIPENDELEO / VIDHIDI VYA KUZINGATIA WAKATI WA TATHMINI

- Muda wa maisha / muda wa programu, mfano miaka 5, 10, n.k.

- Rasilimali zinazopatikana – bajeti zao, mfano rasilimali watu, fedha.

- Lengo la tathmini.

- Njia za ufuatiliaji zilizopo tayari. Ikiwa tuna mfumo wa ufuatiliaji mzuri, programu inaweza isihitaji tathmini ya kati.

- Je, wataathmini wa nje watahusika?

- Wakati wa watu – wanapatikana lini?

- Hali ya hewa – hali ya anga na msimu, mfano wakati unataka kufanya utafiti.

- Wakati wa wafanyakazi wa programu, wizara na mashirika ya nje.

- Mara nyingi ni rahisi kuonyesha kushindwa kuliko mafanikio ya programu, hasa pale ambapo fedha ziko hatarini.

- Sababu ya kuwa si rahisi kwa tathmini kuonyesha mafanikio au kushindwa kwa wakati mmoja inaweza kuchukuliwa kama mafanikio kwa sehemu.

- Mafanikio au kushindwa yana maana tofauti kwa watu tofauti; mfano, miradi ya maji inaweza kusababisha uchafuzi wa mazingira.

- Tathmini inahusisha mambo yanayoweza kuhesabiwa au kupimwa, mfano watu, bidhaa, huduma, kiasi cha malighafi, rasilimali zilizopo, gharama za kifedha, ukubwa wa maeneo yaliyochinjwa, n.k. Haya huitwa vipengele vya kiasi (quantitative aspects) vya tathmini.

- Pia inahusisha vipengele vya ubora (qualitative), mfano huduma, walengwa na watoa huduma.

- Vipengele vya ubora vya tathmini vinahusisha tabia za watu, mitazamo na maadili yao, uwezo, mahusiano, ujuzi, n.k.

- Kipengele cha tathmini ni muhimu kwa sababu husaidia kueleza kwanini programu katika eneo fulani inafanyika kwa namna fulani na kwanini ina nguvu na udhaifu maalumu, matatizo na suluhisho, matokeo yanayotarajiwa na yasiyotarajiwa.

- SABABU ZA KUFANYA TATHMINI

- Kwa ajili ya mafanikio – kuthibitisha / kutathmini kilichopatikana.

- Kutambua maeneo yenye nguvu na udhaifu.

- Kuboresha ufuatiliaji.

- Kuendelea kufadhili programu.

- Kwa ajili ya uchambuzi wa gharama-manufaa – je gharama ni za busara?

- Kwa ajili ya kurudia programu (replication).

- Kwa ajili ya kupanua programu, mfano kutoka jaribio hadi kiwango kikubwa.

- Kwa ajili ya kukusanya taarifa kwa ajili ya upangaji bora, mpangilio na ukubwa.

- Kwa ajili ya msingi wa hoja na uwajibikaji.

- Kwa ajili ya maarifa – kujifunza kitu kipya.

- Kupima maendeleo kulingana na malengo yaliyowekwa.

- Kwa sababu shirika linalofadhili limeomba tathmini ifanywe.

- Kwa sababu mtafiti anataka kujaribu mbinu mpya.

- Kuashiria mwisho wa programu.

- Kwa kulinganisha kati ya mikoa tofauti.

- Tathmini ni kama kuangalia kuona tunaenda wapi na kwa kasi gani, kisha kukadiria lini tutafikia marudio yetu.

- Evaluation is carried out mainly as a way of looking at-

- Human resources

- Financial resources

- Materials

- Information, facts and figures

Inorder to:

- Monitor programme effectiveness

- Consider costs and efficiency.

- Show where charges are needed and help to plan more effectively for the future.

EVALUATION AND FOLLOW UP

What is evaluation of a training programme?

-Evaluation is a process of seeking feedback from the learners and other sponsors, employees, clients, trainers, during or after aspects of the training programme about various aspects of the training programme.

1)Feasibility study is done – no programme in place.

2). Why do we evaluate a training programme

-Evaluation of a training programme helps in assessing the following aspects.

1.  The relevance of the training objectives. Are they relevant to the group of trainees? Are they realistic and achievable?

2. The accomplishment of objectives have the objectives been achieved during the training programme?

3 The appropriateness of the training methodology – has the training designed kept in mind the various considerations of the learners? Are the training methods interested? Eg group discussion, excursions dramatizations, singing, storytelling, case studies demonstration, experimentation.

- Is the environmental conducive to learning, learner friendly eg cleanliness, no distractions, relationship between learner and teacher – confidence.

- Were some methods are more appropriate than others eg. Lecture, oral demonstration.

- The impact of learning in different situations eg work place, market place, home, social meetings eg peers, colleagues. Etc.

3. What to evaluate?

There are various compliments of a training programme that need to be assessed at different intervals of time both during the process of training as well as after the completion of training.

These are:VASK----VALUES, ATTITUDES, SKILLS, KNOWLEDGE

The learner: PAB

a) Attitudinal changes – has the training programme brought any changes in the attitudes and values of the learners.

b)Behavioral changes- have the learners shown any behavioral changes during and within the training programme and even back at home?

c) Performance changes – has the training contributed to any improved performance.

2.Training programme itself

a)Objectives- are they realistic, simple and relevant? Have they been achieved? To what extent?

b)Content (s) – adequate? Meaningful? Relevant to the objectives?

c) Training methods – interesting, appropriate? Facilitating or hampering learning.

d) Time – Is allocated time matching with the scope eg holiday?

e) Trainers – Are the trainers keeping pace with the learners?

- Are they sensitive to the learners needs.

-Are they able to take care of special learners.

- Are the learners fatigued?

f) Learning materials – are they well organized?

- Are they relevant and appropriate to content?

g) Physical equipment – Are  the training facilities comfortable.

- Is the learning accommodation arrangements alright?

- Is the food arrangement satisfactory?

- Does the physical environment facilitate learning or hamper it

A.

Tathmini hufanywa hasa kama njia ya kuangalia:

Rasilimali watu

Rasilimali za kifedha

Vifaa/malighafi

Taarifa, ukweli na takwimu

Ili:

i. Kufuatilia ufanisi wa programu

ii. Kuzingatia gharama na ufanisi

iii. Kutoa eneo la kubadilisha au kuboresha na kusaidia kupanga kwa ufanisi zaidi kwa siku za usoni

TATHMINI NA UFUATILIAJI

Tathmini ya programu ya mafunzo ni nini?

Tathmini ni mchakato wa kutafuta maoni kutoka kwa wanafunzi na wadau wengine, wafanyakazi, wateja, wakufunzi, wakati wa au baada ya vipengele vya programu ya mafunzo kuhusu nyanja mbalimbali za programu hiyo.

Utafiti wa uwezekano (Feasibility study) – hufanywa kabla ya kuwepo kwa programu.

2) Kwa nini tunafanya tathmini ya programu ya mafunzo

Tathmini ya programu ya mafunzo husaidia kutathmini vipengele vifuatavyo:

Umahiri wa malengo ya mafunzo

Je, malengo hayo yanahusiana na kikundi cha wanafunzi?

Je, ni halisi na yanayoweza kufikiwa?

Ufanisi wa malengo

Je, malengo yamefikiwa wakati wa programu ya mafunzo?

Ulinganifu wa mbinu za mafunzo

Je, mafunzo yaliyoundwa yamezingatia mahitaji ya wanafunzi?

Je, mbinu za mafunzo ni za kuvutia? Mfano: majadiliano ya makundi, ziara za shambani/viwandani, michezo ya kuigiza, kuimba, hadithi, tafiti za kesi, maonyesho, majaribio.

Je, mazingira yanayofaa kwa kujifunza, rafiki kwa mwanafunzi? Mfano: usafi, hakuna vikwazo, uhusiano kati ya mwanafunzi na mwalimu – kujiamini.

Je, baadhi ya mbinu zilikuwa bora zaidi kuliko zingine? Mfano: mihadhara, maonyesho ya mdomo.

Athari ya kujifunza katika mazingira tofauti, mfano: mahali pa kazi, sokoni, nyumbani, mikutano ya kijamii, wenzake, wenzake wa kazi, n.k.

3) Nini kinachopaswa kuthaminiwa?

Kuna vipengele mbalimbali vya programu ya mafunzo vinavyopaswa kutathminiwa kwa vipindi tofauti vya muda, wakati wa mafunzo na baada ya kumaliza mafunzo. Hivi ni:

a) Mwanafunzi

Mabadiliko ya mtazamo – Je, programu ya mafunzo imeleta mabadiliko katika mitazamo na maadili ya wanafunzi?

Mabadiliko ya tabia – Je, wanafunzi wameonyesha mabadiliko ya tabia wakati wa na ndani ya mafunzo na hata nyumbani?

Mabadiliko ya utendaji – Je, mafunzo yamechangia katika utendaji bora?

b) Programu ya mafunzo yenyewe

Malengo – Je, ni halisi, rahisi na yanayohusiana? Yamefikiwa kwa kiwango gani?

Mada – Je, ni ya kutosha? Yenye maana? Inahusiana na malengo?

Mbinu za mafunzo – Je, ni za kuvutia, zinazofaa? Zinasaidia au kuzuwia kujifunza?

Muda – Je, muda uliotolewa unaendana na wigo wa mafunzo, mfano likizo?

Wakufunzi – Je, wakufunzi wanaendana na kiwango cha wanafunzi?

Je, wanahisi mahitaji ya wanafunzi?

Je, wanaweza kushughulikia wanafunzi maalumu?

Je, wanafunzi wako na uchovu?

Vifaa vya kujifunzia – Je, vimepangwa vizuri?

Je, vinahusiana na mada?

Vifaa vya kimwili – Je, mahali pa mafunzo ni pazuri?

Je, makazi ya kujifunzia yamepangwa vizuri?

Je, mpangilio wa chakula uko sawa?

Je, mazingira ya kimwili yanasaidia kujifunza au kuzuia?

METHODOLOGY OF EVALUATION

-There are two main methods of evaluation. These are:

1. The traditional methods

2. Participatory method – trainee centred.

TRADITIONAL METHOD.

- It is evaluator centred.

- Practices passive involvement of the trainee.

- Information is generally collected/gathered on the main content part  eg books , materials and records kept, relevant materials/literature (evaluator centred)

- The process part methodology, part, traditional counselling which gives the mode of learning is neglected.

- It is a unilateral where by the results benefit the trainers only, it is one way.

- The evaluation benefits the trainers, do not share with the trainees, keep information to themselves.

PARTICIPATORY METHOD

1There is involvement of the trainees/active.

2 It is interactive process

3. There is effective communication which contributes to effective learning process.

4. Teachers/trainers are able to identify difficulties.

5. It is beneficial to trainers and trainees (learners)

6. There is the feeling of ownership.

7. It is none judgemental in nature

8. It looks at the strengths and weaknesses.

9. It is a more reliable process because information is gathered from different dimension /meaningful.

CHARACTERISTICS OF PARTICIPATORY EVALUATION

- There is a lot of involvement of trainees/learners and shared control, none is dominating the evaluation process and making decision alone.

- It is developmental – it is for personal gain/growth.

- Awareness raising – get aware of their strengths and weaknesses and what is going on in the training programme at all stages.

- It is empowering trainees – has full information so feels empowered.

- Mobilization – Easy to involve the learners in the programme. They are motivated towards contributing to the effectiveness of the training programme.

SOURCES OF INFORMATION

It is important to obtain valid and authentic information for evaluations, individual learners have their own indicators and standards for evaluating therefore, evaluation feedback can be sort from different sources. These are either primary or secondary sources.

PRIMARY SOURCES

-This is where we get first-hand information. They can be the learner himself/herself.

-Trainers interact with the learners and gather information.

From colleagues – others who know the learners and trainers well.

SECONDARY SOURCES

1.From records of the training and related activities eg attendance register performance, sow, progress records, discipline records.

2. Learning materials/literature related.

3. Specific reports of the organization.

4. Diaries – maintained by the trainees and trainers.

WHEN EVALUATION CAN BE DONE

Types of evaluation (when)

- Daily evaluation

- Mid-term evaluation

- End –term evaluation

- Evaluation at specified time after training

DAILY EVALUATION

-Daily evaluations are helpful for identifying and resolving problems as they arise.

One method of conducting this is to inform a steering committee members either volunteer to be on the committee or are chosen by the group members.

- Membership could also be on a rotational basis.

- The committee members seek information, reactions, feelings and suggestions from other members of the group throughout the day.

- - They also keep track on what is happening during the session.

- At the end of the day the members hold a meeting and share their findings based on the concerned shared solutions can be developed jointly and appropriate responsibilities can be taken to effect their changes.

Advantage

-The implication of such a process of evaluation are-

i)Both the trainer and trainee (learner) take the process seriously.

i) Dialogue between the learners and trainers is carried out daily. Different issues that would have otherwise interfered with the process of learning get aired and resolved.

iii) Problems get solved as they arise

Both learners and trainers assume joined responsibility for the management of the training.

v) Daily course correction can take place to keep the learning process on track.

-sometimes less structures ways of daily evaluation can also be used eg spending some time eg 1 hr in the morning on the raised concerned issues (recap) can be done to facilitate daily evaluation.

A. MBINU ZA TATHMINI (METHODOLOGY OF EVALUATION)

Kuna njia kuu mbili za tathmini:

Njia za kitamaduni (Traditional methods)

Njia ya ushirikishwaji – inayomlenga mwanafunzi (Participatory method – trainee centred)

NJIA ZA KITAMADUNI (TRADITIONAL METHOD)

Inazingatia mtathmini (evaluator centred).

Inahusisha mwanafunzi kwa njia isiyo ya moja kwa moja (passive involvement).

Taarifa hukusanywa hasa kwenye sehemu kuu za maudhui, mfano vitabu, vifaa, rekodi zilizohifadhiwa, nyaraka muhimu (evaluator centred).

Mbinu za mchakato wa kujifunza (methodology part) au ushauri wa kitamaduni (traditional counselling) zinazotoa mtindo wa kujifunza hazizingatiwi.

Ni upande mmoja (unilateral) ambapo matokeo yanayofaidi ni kwa wakufunzi tu.

Tathmini inafaidi wakufunzi, hishiriki na wanafunzi, na wanahifadhi taarifa kwao wenyewe.

NJIA YA USHIRIKISHWAJI (PARTICIPATORY METHOD)

Kuna ushiriki wa wanafunzi/wanachukua hatua (active involvement).

Ni mchakato wa mazungumzo (interactive process).

Kuna mawasiliano mazuri ambayo huchangia ufanisi wa kujifunza.

Walimu/wakufunzi wanaweza kubaini changamoto.

Inafaidi wakufunzi na wanafunzi.

Kuna hisia ya umiliki wa mafunzo.

Haijakandamiza (non-judgemental).

Inazingatia nguvu na udhaifu.

Ni mchakato unaoaminika zaidi kwa sababu taarifa hukusanywa kutoka katika vipengele tofauti na zinazoleta maana.

SIFA ZA TATHMINI YA USHIRIKISHWAJI (CHARACTERISTICS OF PARTICIPATORY EVALUATION)

Kuna ushiriki mkubwa wa wanafunzi na udhibiti wa pamoja, hakuna anayedominika na kufanya maamuzi peke yake.

Ni ya kimaendeleo – inafaa kwa ukuaji binafsi.

Kuongeza uelewa – wanafunzi wanatambua nguvu na udhaifu wao na kinachoendelea katika programu ya mafunzo katika hatua zote.

Inawawezesha wanafunzi – wanapata taarifa zote hivyo wanahisi kuwa na nguvu.

Uhamasishaji – Rahisi kuhusisha wanafunzi katika programu. Wanahamasishwa kuchangia katika ufanisi wa mafunzo.

VYANZO VYA TAARIFA (SOURCES OF INFORMATION)

Ni muhimu kupata taarifa sahihi na za kweli kwa ajili ya tathmini. Kila mwanafunzi ana viashiria na viwango vyake vya kutathmini, hivyo mrejesho wa tathmini unaweza kupatikana kutoka vyanzo tofauti. Vyanzo hivi vinaweza kuwa vya msingi (primary) au vya pili (secondary).

VYANZO VYA MSINGI (PRIMARY SOURCES)

Hapa ndipo tunapata taarifa za kwanza. Mwanafunzi mwenyewe anaweza kuwa chanzo.

Wakufunzi wanawasiliana na wanafunzi na kukusanya taarifa.

Kutoka kwa wenzake – wengine wanaojua mwanafunzi na wakufunzi vizuri.

VYANZO VYA PILI (SECONDARY SOURCES)

Kutoka kwenye rekodi za mafunzo na shughuli zinazohusiana, mfano: rejista ya mahudhurio, utendaji, SOW, rekodi za maendeleo, rekodi za nidhamu.

Vifaa vya kujifunzia/nyaraka zinazohusiana.

Ripoti maalumu za shirika.

Daftari – yanayohifadhiwa na wanafunzi na wakufunzi.

WAKATI WA KUFANYA TATHMINI (WHEN EVALUATION CAN BE DONE)

Aina za tathmini:

Tathmini ya kila siku (Daily evaluation)

Tathmini ya katikati ya kipindi (Mid-term evaluation)

Tathmini mwishoni mwa kipindi (End-term evaluation)

Tathmini wakati maalumu baada ya mafunzo

TATHMINI YA KILA SIKU (DAILY EVALUATION)

Tathmini za kila siku husaidia kubaini na kutatua matatizo yanapojitokeza.

Njia moja ni kumjulisha wanachama wa kamati ya uendeshaji, ambao wanaweza kujitolea au kuchaguliwa na kundi.

Uanachama unaweza pia kuwa kwa mzunguko (rotational basis).

Wanachama wa kamati hukusanya taarifa, hisia, maoni na mapendekezo kutoka kwa wanachama wengine wa kundi siku nzima.

Pia hufuata kinachoendelea wakati wa kikao.

Mwisho wa siku, wanachama huandaa mkutano na kushirikiana matokeo yao, na kuunda suluhisho kwa pamoja na kuchukua majukumu husika.

Faida:

Matokeo ya mchakato huu wa tathmini ni:

i) Wakufunzi na wanafunzi huchukua mchakato kwa umakini.

ii) Mazungumzo kati ya wanafunzi na wakufunzi hufanyika kila siku. Masuala tofauti yanayoweza kuingilia mchakato wa kujifunza yanajadiliwa na kutatuliwa.

iii) Matatizo yanatatuliwa kadri yanavyojitokeza.

iv) Wanafunzi na wakufunzi wanashirikiana kwa pamoja katika usimamizi wa mafunzo.

v) Marekebisho ya kila siku yanaweza kufanyika ili mchakato wa kujifunza uende kwa usahihi.

Wakati mwingine njia zisizo rasmi za tathmini ya kila siku zinaweza kutumika, mfano kutumia saa 1 asubuhi kwa kurudia masuala yaliyotolewa ili kuwezesha tathmini ya kila siku.

MID-TERM EVALUATION.

-It is conducted at the middle of a training programme.

- This is a vital stage for consolidating the present learning, giving opportunity for catharsis (raising them to alevel of sympathy/emotion) self-introspection,reflecting yourself) to take place and ensuring relevant direction for the remaining period of training.

-  In a group, individual learners can share their feelings, what they feel concerned about anything that they have learnt, their reactions, anything new they would like to learn. A sense of where the group is can be gauged/judged this way.

-mid-term review can be done orally through a questionnaire and or individual interview. The results of the evaluation can be both at the individual and group levels. If some individual and group levels, if some individual learners are feeling low and disconnected they can be supported and encouraged by the co-learners and trainers.

- Modification can also be brought about in the topic, phase of the training programme, re-orientation of sessions for the entire group of learners.

3. End term evaluation (immediately after the training)

-As soon as the training is completed an evaluation is helpful to access the impact of the training impression when experiences are fresh in the minds of the learners and this information must be collected or else it will get lost.

- the evaluation can be done through sharing questionnaires, small group meetings and individuals, conferences, suggestions for future training programme can also be sought at this stage.

4.Evaluation at specified interval after the training programme.

- Back home after the training programme the learners through their practice can draw some additional insight in to the training programme.

-to strengthen future training programs such insights are very essential. The method of sharing the feedback can be decided upon by the learners and trainers. It could be through a questionnaire or face to face dialogue or both.

- Many at times evaluation conducted after three to six months of the training programme can provide a realistic assessment of learning.

- Learners assessment immediately after training programme may be rejected depending upon the immediacy of experiences. Post training evaluation (several months later) provides a distance feedback from that training experience and hence a more realistic and balanced assessment is possible.

- In any case it is possible and sometimes desirable to conduct this evaluation at all the four stages mentioned above.

RECORDS

What are records?

- Formally written information related to a various aspects of the programme eg data, analysis, preserved for future use.

What kind of data can be collected using the instrument?

- Photograph data

- Tape recorded

- Data reports

- Records of activities taking place in the programmes e.g. progress records attendance records, meeting minutes.

- -Records on resource materials.

- Schedules of the activities eg timetables term dates, administrative records eg work ticket, log books, financial records eg receipts books fees registers, cash book,invoices payment, vouchers, ledger etc.

- Population records/enrolment data eg students and teachers/staff support staff(personal records).

- Records of physical facilities in the institution – inventory book eg personnel records- staff.

Why do we administer records/instruments

-To monitor/access the programme progress of the students/learners

-Discover the weakness and strength of the programme.

-can be obtained from photographs?

Tape records, audio visual etc

NB: In groups let them discuss the instrument

A. TATHMINI YA KATI YA KIPINDI (MID-TERM EVALUATION)

Hufanywa katikati ya programu ya mafunzo.

Hii ni hatua muhimu kwa kuimarisha kile kilichojifunza hadi sasa, kutoa nafasi ya kuchukua hisia/kuchambua ndani ya nafsi (catharsis, self-introspection, reflection) na kuhakikisha mwelekeo unaofaa kwa kipindi kilichobaki cha mafunzo.

Katika kundi, wanafunzi wanaweza kushirikiana hisia zao, kile wanachohisi, wanachohusika nacho, kile walichojifunza, hisia zao, na vitu vipya wanavyotaka kujifunza. Hii inasaidia kutambua hali ya kundi kwa ujumla.

Mapitio ya kati yanaweza kufanyika kwa mdomo kupitia dodoso au mahojiano ya mtu mmoja mmoja. Matokeo ya tathmini yanaweza kuwa kwa viwango vya mtu binafsi na vya kundi. Ikiwa baadhi ya wanafunzi wanajihisi chini au kutokuwa sehemu ya kundi, wanaweza kuungwa mkono na kuhamasishwa na wenzake na wakufunzi.

Marekebisho pia yanaweza kufanywa kwenye mada, hatua ya programu, au upangaji upya wa vikao kwa kundi lote la wanafunzi.

3. TATHMINI MWISHO WA KIPINDI (END-TERM EVALUATION – BAADA YA MAFUNZO)

Mara tu mafunzo yanapomalizika, tathmini ni muhimu kwa kutathmini athari za mafunzo wakati uzoefu bado uko safi akilini mwa wanafunzi. Taarifa hii lazima ikusanywe mapema, vinginevyo itapotea.

Tathmini inaweza kufanywa kwa kushiriki dodoso, mikutano midogo ya makundi, mazungumzo ya mtu mmoja mmoja, mikutano, na pia kuomba mapendekezo kwa ajili ya programu za mafunzo za baadaye.

4. TATHMINI KWA WAKATI MAALUM BAADA YA MAFUNZO

Baada ya kurejea nyumbani, wanafunzi kupitia mazoezi yao wanaweza kupata uelewa zaidi juu ya programu ya mafunzo.

Kwa kuimarisha programu za mafunzo za siku za usoni, uelewa huu ni muhimu sana. Njia ya kushiriki mrejesho inaweza kuamuliwa na wanafunzi na wakufunzi; inaweza kuwa kupitia dodoso, mazungumzo ya uso kwa uso, au zote mbili.

Mara nyingi, tathmini iliyofanywa miezi 3 hadi 6 baada ya mafunzo inaweza kutoa ukadiriaji halisi wa kujifunza.

Tathmini ya wanafunzi mara baada ya mafunzo inaweza kupuuzwa kutokana na ufupi wa uzoefu. Tathmini baada ya mafunzo (miezi kadhaa baadaye) hutoa mrejesho wa mbali kutoka kwa uzoefu huo na hivyo kutoa ukadiriaji halisi na sawa zaidi.

Kwa hali yoyote, inawezekana na wakati mwingine inafaa kufanya tathmini hii katika hatua zote nne zilizotajwa hapo juu.

REKODI (RECORDS)

Rekodi ni nini?

Taarifa zilizopangwa rasmi zinazohusiana na vipengele mbalimbali vya programu, mfano data, uchambuzi, zilizohifadhiwa kwa matumizi ya baadaye.

Ni aina gani ya data inaweza kukusanywa kwa kutumia vifaa vya rekodi?

i) Data za picha (photograph data)

ii) Rekodi zilizorekodiwa (tape recorded)

iii) Ripoti za data (data reports)

Rekodi za shughuli zinazofanyika kwenye programu, mfano: rekodi za maendeleo, rejista ya mahudhurio, daftari la mikutano.

Rekodi za rasilimali/malighafi.

Ratiba za shughuli, mfano: ratiba za masomo, tarehe za kipindi, rekodi za utawala, tiketi za kazi, daftari la log, rekodi za kifedha, mfano: vitabu vya mapokezi, rejista ya ada, daftari la fedha taslimu, ankara, vibali, ledger, n.k.

Rekodi za idadi ya watu/kujiandikisha, mfano wanafunzi, walimu/wafanyakazi, wafanyakazi wa msaada (rekodi za kibinafsi).

Rekodi za miundombinu ya shule – kitabu cha hesabu, mfano rekodi za wafanyakazi.

Kwa nini tunahifadhi rekodi/vifaa?

Kufuatilia/kuhakiki maendeleo ya programu ya wanafunzi/wanafunzi.

Kugundua udhaifu na nguvu za programu.

Taarifa inaweza kupatikana kutoka kwa picha, rekodi za sauti, midia ya kuona na kusikia (audio-visual), n.k.

Kumbuka: Katika makundi, wacha wajadili vifaa vya kurekodi (instrument).

ADVANTAGES

-Gives organized records

-Protected

- future reference

- show state for performance

-used for evidence recording and promotion

DISADVANTAGES

-incase of misplacement

- inconvenience

- Insecurity

-Prone to damage

-Assessment problem.

GROUP 1

QUESTIONNAIRE

WHAT IS A QUESTIONNAIRE?

It is a document with simple and precise objectives structured questions used researcher to collect specified information or data.

-Are of two types closed ended and open- ended on specific topic which can collect qualitative and quantitative data.

- Has a list of written items/statements.

WHAT KIND OF DATA CAN BE COLLECTED

-Qualitative and quantitative data eg attitudes values, feelings, age, gender pop of learners etc.

How can the instrument be administered?

- Self- administered – face to face/paper and pencil questions administered.

- Mailing – Mail questionnaires – computer administration

- Un -directive computerized administration – next items based on the group administer respondents estimated ability or traits of respondents

What are the merits?

-easy to administer

- It is more reliable and accurate, connect information is given.

-Can be used for future reference

- Confidence is maintained

- Saves time/cost effective.

-Provides evidence.

-Pan reach distance people/learners.

- Can cross-validate the information within a questions

-Collects in – depth information,

Demerits

- Information in most cases is not interactive.

- May be bias/subjective

- It is self-restrictive because the space is also limited.

- May lead to misleading questions and may not justify the information.

- Return rate may be low eg when mailed.

- Not easy to analyze/does not save time

- Not answer all questions.

- Can only be used or administered by literate people.

GROUP II

OBSERVATION GUIDE

What is observation guide?

-Is a list of items particularly questions and statements that guide a process of observation in gathering data.

-At times we have participatory observation where we have questions.

- the items lead to realization of the objectives of the observation.

- The observation process of involves the use of all senses

What data do we collect?

- The delivery/mastery of content.

- Attitudes – interest

- Behavior changes eg subjects that need application formula)

- Observe the resources being used are they appropriate and relevant.

- Interpretation

- Discipline – interaction between teachers and learners

- Acceptance or rejection of new products through reaction

- Learning environment – appropriateness intimidating harassed etc.

- Achievement of the objectives

- Content – relevant, mastery flow.

- Age appropriateness in relation to the t/c resources.

HOW TO ADMINISTER

1 Involvement eg taking notes, role play, field visit data

2. Participatory observation. Non participatory, tape recording

MERITS

- Done in a natural setting / is real

- Give accurate perspective

- Validity /more valid there and then

- Specific information is gathered

- Not open to socially acceptable responses

- Non- participatory gives a good picture

- Can be interactive

- Able to observe complex relations and capture them.

- Highly reliable

DEMERITS

-Prejudice/bias/ prejudgment/ subjective

- Pretence

- Emotional involvement

-Time consuming

-May make instant decisions without looking at the underlying factors.

-Does not cater for the poor/eyesight/blind

-Cannot observe past events/processes historical.

INTERVIEW GUIDE SCHEDULE

-Face to face method of collecting data

-Telephone interview

-used in the field to cross validate information.

A. MANUFAA NA HASARA YA REKODI (ADVANTAGES & DISADVANTAGES)

MANUFAA (ADVANTAGES)

Hutoa rekodi zilizopangwa vizuri.

Zinalindwa.

Kwa kumbukumbu za siku za usoni.

Kuonyesha hali ya utendaji.

Kutumika kama ushahidi na kwa maendeleo/promotion.

HASARA (DISADVANTAGES)

Ikiwa zikapotea.

Kutokuwa rahisi kutumia.

Usalama mdogo.

Rahisi kuharibika.

Shida za tathmini.

KUNDI LA 1 – DODOSO (QUESTIONNAIRE)

DODOSO NI NINI?

Ni hati yenye malengo rahisi na maswali yaliyoandikwa kwa mpangilio maalumu inayotumika na mtafiti kukusanya taarifa maalumu au data.

Kuna aina mbili: yenye majibu yaliyofungwa (closed-ended) na yenye majibu ya wazi (open-ended) juu ya mada maalumu, ambazo zinaweza kukusanya data ya ubora (qualitative) na idadi (quantitative).

Ina orodha ya vipengele/kauli zilizowekwa.

DATA GANI INAWEZA KUKUSANYWA?

Data za ubora na idadi, mfano: mitazamo, maadili, hisia, umri, jinsia, idadi ya wanafunzi, n.k.

VIFAA VINAWEZA KUTUMIKAJE?

i) Kujijiendesha mwenyewe (Self-administered) – uso kwa uso au karatasi na penseli.

ii) Kupitia barua (Mailing) – Dodoso kupitia barua au kompyuta.

Usimamizi wa kompyuta usio na mwelekeo (Un-directive computerized administration) – kipengele kinachofuata kinategemea uwezo uliokadiriawa wa watakaojibu.

MANUFAA YA DODOSO

Rahisi kutekeleza.

Zaidi ya kuaminika na sahihi, taarifa sahihi zinatolewa.

Inaweza kutumika kama kumbukumbu ya siku za usoni.

Kuimarisha ujasiri.

Huhifadhi muda na gharama.

Hutoa ushahidi.

Inaweza kufikia watu/wanafunzi walioko mbali.

Inaweza kuthibitisha taarifa ndani ya maswali.

Inakusanya taarifa kwa kina.

HASARA YA DODOSO

Taarifa mara nyingi si ya ushirikiano.

Inaweza kuwa na upendeleo (bias/subjective).

Inajizuia yenyewe kwa nafasi ndogo ya jibu.

Inaweza kusababisha maswali yanayopotosha na yasiyothibitisha taarifa.

Kiwango cha kurudishwa kwa dodoso kinaweza kuwa kidogo, mfano barua.

Si rahisi kuchambua/haiahidishi kuokoa muda.

Haiwezi kujibu maswali yote.

Inaweza kutumika na watu waliyojua kusoma na kuandika tu.

KUNDI LA II – MWONGOZO WA UCHUNGUZI (OBSERVATION GUIDE)

MWONGOZO WA UCHUNGUZI NI NINI?

Ni orodha ya vipengele, hasa maswali na kauli zinazoongoza mchakato wa uchunguzi wa kukusanya data.

Wakati mwingine tunakuwa na uchunguzi wa ushirikishwaji, ambapo kuna maswali.

Vipengele vinasaidia kufanikisha malengo ya uchunguzi.

Mchakato wa uchunguzi unahusisha matumizi ya hisia zote (all senses).

DATA GANI INAKUSANYWA?

Uwasilishaji/utimilifu wa maudhui.

Mitazamo – shauku/maslahi.

Mabadiliko ya tabia, mfano masomo yanayohitaji kutumia fomula.

Kuangalia rasilimali zinazotumika – ni sahihi na zinazofaa?

Tafsiri (interpretation).

Nidhamu – mwingiliano kati ya walimu na wanafunzi.

Kukubali au kukataa bidhaa mpya kupitia hisia/majibu.

Mazingira ya kujifunzia – yanayofaa, yenye kuogopesha, kuchukizwa, n.k.

Ufikaji wa malengo.

Maudhui – yanayohusiana, utimilifu, mtiririko.

Umri unaofaa kwa rasilimali za mwalimu/mwanafunzi.

JINSI YA KUTUMIA MWONGOZO

Ushiriki – kuchukua noti, kuigiza (role play), ziara shambani, data ya utafiti.

Uchunguzi wa ushirikishwaji (Participatory observation) au usio wa ushirikishwaji, kurekodi sauti.

MANUFAA

Hufanyika katika mazingira halisi/ni ya kweli.

Hutoa mtazamo sahihi.

Validity / inakuwa halisi pale pale.

Taarifa maalumu zinakusanywa.

Haiwezi kudanganywa na majibu yanayokubalika kijamii.

Uchunguzi usio wa ushirikishwaji hutoa picha nzuri.

Inaweza kuwa ya ushirikiano.

Inawezesha kuona uhusiano mgumu na kuurekodi.

Zaidi ya kuaminika.

HASARA

Upendeleo/bias/maamuzi ya awali/subjective.

Kujifanya (Pretence).

Ushirikiano wa kihisia (Emotional involvement).

Inachukua muda.

Inaweza kufanya maamuzi ya haraka bila kuangalia sababu za msingi.

Haizingatii maskini/watoto wenye matatizo ya kuona/wanaoishi na ulemavu wa kuona.

Haiwezi kuangalia matukio ya zamani/historia.

MWONGOZO WA MAHOJI (INTERVIEW GUIDE SCHEDULE)

Njia ya uso kwa uso ya kukusanya data.

Mahojiano kwa simu.

Inatumiwa kwa utafti kuthibitisha taarifa.

TYPES OF DATA

Merits and demerits similar to focus group discussion

HOW THIS IS ADMINISTERED

Oral interview

Competency test

Phone/call skype call

Assessment centre (military recruitment)

FOCUS GROUP DISCUSSION GUIDE

What are they?

-This is a group charged with the responsibility of making an assessment of particular aspects of a phenomenon.

The group/individuals should have been informed on what to discuss.

-The questions are focusing on a particular aspect eg school fees guides.

-The group must be homogenous 6-12 people.

-There should be a moderator/facilitator and assistants. The focus is on the topic.

-The people must have something in common.

-Time is almost 2 hours target group eg parents called to discuss on issues pertaining their school/education.

What type of data

QL – attitudes, attributes skills values and knowledge perception.

QN- No. of trainers, trainees, tele-conferencing enrolment.

QL aspect is used.

HOW TO ADMINISTER

-Organize your group

-Identify the focus group

-Identify an assistant/facilitator

-more to the session one by one from the group members helped by the facilitator.

-Report is taken from the interaction.

-It is a greater process.

MERITS

-Can be used by the illiterate and literate.

- There is firsthand information.

- Sharing of experiences.

-Ownership – sense of ownership

-Everybody is empowered/knowledge is shared.

-Different talents and skills can be exploited and developed

-Enables one to collect more detailed information.

- It is an interactive method and can be used eg questionnaire record what you see or hear able to follow non-verb and clues.

DEMERITS

-Some members may dominate the discussion.

- It takes relatively longer time –time consuming.

-disagreement may bound to occur. This may lengthen the time but as the facilitator you should control.

- It limits people with certain skills eg. Interviewing skills.

-members of disunity can personalize issues thus amber the discussion.

-can be expensive.

-It is limited only to those empowered to speech unless you mute specialists.

-Some issues against their norms may be shied on.

CHECKLIST

WHAT IT IS?

It is a special type of a questionnaire that has horizontal column.

-It helps the questionnaires to identify the feeling/qualities/ respondents

| Qualities | Very strong | Strongly | Lightly | Not sure |
| --- | --- | --- | --- | --- |
| Educational qualities |  |  |  |  |
| Experience |  |  |  |  |

TYPE OF DATA

QL and QN –performance physical facilities attitudes, motivation, level satisfaction

ADVANTAGES

Ensures items are not forgotten

Guidelines are followed.

-Helps to prevent error in a programme

-Ensures consistency and competence

HOW TO ADMINISTER

-Through groups, HoDs, members of staff.

- Issue the checklist personally/self- administration.

-Mail the checklist.

-Through interview/individual

Merits

-The information gathered is easy to analyze.

Easy to code.

-Responses are immediate/easy to administer.

-Responses are guided so irrelevancy is avoided.

-Not too involving/in expensive.

-Saves time.

-Leads to under access/analyze the data for future use/different time.

Demerits

-Some information may be left out in the design.

-Its responses are too restrictive/explanation is not allowed.

-Sometimes the checklist may be subjective in the design and some information may be left if he/she has perception of his/her own.

-The responses may be tempted to make ticks without much thinking.

-Feelings are not quantifiable

-Nb: Best way is to use a variety of methods to get complete information.

A. AINA ZA DATA (TYPES OF DATA)

Manufaa na hasara yake ni sawa na mjadala wa kikundi maalumu (focus group discussion).

JINSI INAFANYWA

Mahojiano kwa mdomo (Oral interview)

Mtihani wa ujuzi/utaalamu (Competency test)

Simu au Skype call

Kituo cha tathmini (Assessment centre), mfano ajira za kijeshi (military recruitment)

MWONGOZO WA MJADALA WA KIKUNDI MAALUMU (FOCUS GROUP DISCUSSION GUIDE)

Ni nini?

Huu ni kikundi kilichopewa jukumu la kutathmini vipengele maalumu vya jambo fulani.

Kikundi/watu binafsi wanapaswa kuwa wamejulishwa kuhusu kile cha kujadili.

Maswali yanazingatia kipengele maalumu, mfano: mwongozo wa ada za shule.

Kikundi lazima kiwe homogeneous (6-12 watu).

Panapaswa kuwepo mdhibiti/fasiliata (moderator/facilitator) na wasaidizi. Umakini ni kwenye mada.

Watu wanapaswa kuwa na jambo fulani la pamoja.

Muda ni takriban masaa 2, mfano wazazi wanaitwa kujadili masuala yanayohusu shule/elimisha.

Aina ya data

QL (Qualitative) – mitazamo, sifa, ujuzi, maadili, maarifa, mtazamo.

QN (Quantitative) – idadi ya wakufunzi, wanafunzi, tele-conferencing, usajili.

Kipengele cha QL kinatumiwa.

JINSI YA KUTUMIA

Panga kikundi chako.

Tambua kikundi maalumu.

Tambua msaidizi/fasiliata.

Kila mwanachama anashiriki mmoja baada ya mwingine, akiungwa mkono na fasiliata.

Ripoti hutolewa kutokana na mwingiliano.

Ni mchakato mkubwa.

MANUFAA

Inaweza kutumika na wasomi na wasio na elimu rasmi.

Taarifa ni za moja kwa moja (firsthand information).

Kushirikiana uzoefu.

Umiliki – hisia ya kumiliki programu.

Kila mtu ana nguvu/kuna ujuzi unaoshirikishwa.

Vipaji na ujuzi tofauti vinaweza kutumika na kuendelezwa.

Inasaidia kukusanya taarifa kwa kina zaidi.

Ni njia ya ushirikiano na inaweza kutumika pamoja na dodoso, kurekodi kile unachoona au kusikia, kufuatilia ishara zisizo za maneno.

HASARA

Baadhi ya wanachama wanaweza kudominisha mjadala.

Inachukua muda mrefu.

Migongano inaweza kutokea, hivyo muda unaweza kuongezeka lakini fasiliata anapaswa kudhibiti.

Inalenga wale wenye ujuzi fulani, mfano: ujuzi wa mahojiano.

Wanaokosa mshikamano wa kikundi wanaweza kuibua migongano binafsi.

Inaweza kuwa ghali.

Inalenga wale walio na uwezo wa kuzungumza, isipokuwa kama utafanya mtaalamu kimya.

Masuala yanayopingana na kanuni zao yanaweza kuepukwa.

CHECKLIST (ORODHA YA KUKAGUA)

Ni nini?

Ni aina maalumu ya dodoso lenye safu wima (horizontal column).

Inasaidia kuonyesha hisia/sifa za waliojibu.

Sifa	Nguvu sana	Nguvu	Kidogo	Sijui

Sifa za kielimu

Uzoefu

Aina ya data

QL na QN – utendaji, miundombinu, mitazamo, motisha, kiwango cha kuridhika.

MANUFAA

Inahakikisha vipengele havisahauwi.

Mwongozo unafuatwa.

Husaidia kuzuia makosa katika programu.

Inahakikisha uthabiti na ujuzi.

JINSI YA KUTUMIA

Kupitia makundi, Wakurugenzi wa Idara (HoDs), wanachama wa wafanyakazi.

Toa checklist binafsi / kujijiendesha.

Kutuma checklist kwa barua.

Kupitia mahojiano/mtu mmoja mmoja.

MANUFAA YA CHECKLIST

Taarifa zinazokusanywa ni rahisi kuchambua.

Rahisi kuandikia msimbo (code).

Majibu ni ya haraka / rahisi kutekeleza.

Majibu yanasimamiwa, hivyo yasiyo husiana yanaepukwa.

Si ngumu kutumia / gharama si kubwa.

Huhifadhi muda.

Husaidia kutathmini data kwa matumizi ya siku za usoni.

HASARA YA CHECKLIST

Baadhi ya taarifa inaweza kuachwa katika muundo.

Majibu ni makali sana / maelezo hayaorodheshwi.

Wakati mwingine checklist inaweza kuwa subjective na baadhi ya taarifa inaweza kuachwa kutokana na mtazamo wa mwajibu.

Majibu yanaweza kuchukuliwa haraka bila kufikiri sana.

Hisia haiwezi kupimika kwa idadi.

Kumbuka: Njia bora ni kutumia mchanganyiko wa mbinu ili kupata taarifa kamili.

Follow-up

This implies to any process of interventions and support provided to an individual and/or a group to further/enhance their learning process for a specified period of time, following the training programme.

-Everything that is done by learners or trainers after the training programmed does not constitute follow-up. Thus follow up implies to activities carried out to support the learning process after the training programme within a given time frame.

Significance of follow-ups.

- Follow-up extends and re-news the learning contract that the learners developed during training programme.

- The contract can be with him/herself with co-learners as well as with trainers.

- Follow-up to a training programme can be used for several purposes.

-provides support and encouragement, knowledge and resources needed to implement the learning the learner acquired during the training programme.

3 Can help to define additional learning needs during the period immediately after the training programme – to that extent it helps to continue with the learning process by bringing our new learning needs.

4 It is used to assess the training programme and its impact on the learners work and organization. Thus helps the trainer in re-designing future training programmes.

5 It provides an opportunity for the learner to consolidate their own experiences acquired during the training programme.

6  In a broad sense of follow-up can all be used strategically. If training has large objectives of social change, follow-up can be used in a strategic way to.

i) Foster a feeling of sociality among like-minded activists and organisations.

ii) Sustain the process and effort of cadre building and formation of networks.

- Strengthen formation of small groups and facilitate a process of building larger and stronger organisations.

Methods of follow-ups

Follow-up can be conducted in different ways. It can be planned different for each learner. It can also be done for the entire learners, it can be done for, a selected group as well.

-Methods of follow-up depends on its purpose and groups of learners as follow.

a) Direct method –This entails face to face interaction among learners themselves and between learners and trainers (field visit)

b)Indirect method- do not entail face to face conduct

-Can be done through correspondence eg news letters, questions or send you questions /her mail them with answers.

c) Combination of the two methods:

-Direct methods are generally more stimulating and supportive but require much greater time and resources indirect methods are relatively inexpensive and can cover a larger set of learning.

A. UFUATILIAJI (FOLLOW-UP)

Maana ya Ufautiliaji

Hii inahusu mchakato wowote wa kuingilia kati na kutoa msaada kwa mtu mmoja au kikundi ili kuendeleza au kuimarisha mchakato wao wa kujifunza kwa kipindi maalumu baada ya programu ya mafunzo.

Kila kitu kinachofanywa na wanafunzi au wakufunzi baada ya mafunzo sio ufuatiliaji. Hivyo basi, ufuatiliaji unahusisha shughuli zinazofanywa kusaidia mchakato wa kujifunza baada ya programu ya mafunzo ndani ya muda uliotolewa.

Umuhimu wa Ufautiliaji

Kuendeleza na kufanya upya mkataba wa kujifunza ulioundwa na wanafunzi wakati wa mafunzo.

Mkataba huu unaweza kuwa na yeye mwenyewe, wenzake (co-learners), na wakufunzi.

Ufautiliaji wa programu ya mafunzo unaweza kutumika kwa madhumuni mbalimbali:

Kutoa msaada na motisha, maarifa na rasilimali zinazohitajika ili kutekeleza kile kilichojifunzwa na mwanafunzi wakati wa mafunzo.

Inaweza kusaidia kutambua mahitaji ya ziada ya kujifunza baada ya programu ya mafunzo – kwa kiasi hicho inasaidia kuendeleza mchakato wa kujifunza kwa kuleta mahitaji mapya ya kujifunza.

Inatumiwa kutathmini programu ya mafunzo na athari zake kwa kazi na shirika la mwanafunzi. Hivyo inasaidia wakufunzi kupanga upya programu za mafunzo za siku za usoni.

Inatoa fursa kwa mwanafunzi kuimarisha uzoefu wake binafsi alioyapata wakati wa mafunzo.

Kwa maana pana, ufuatiliaji unaweza kutumika kistratejia. Ikiwa mafunzo yana malengo makubwa ya mabadiliko ya kijamii, ufuatiliaji unaweza kutumika kistratejia kwa:

i) Kuongeza hisia za kijamii miongoni mwa wanaharakati na mashirika yenye mtazamo sawa.

ii) Kuendeleza mchakato na juhudi za kuunda rika na mtandao wa ushirikiano.

iii) Kuimarisha uundaji wa makundi madogo na kuwezesha mchakato wa kujenga mashirika makubwa na yenye nguvu.

Njia za Ufautiliaji

Ufautiliaji unaweza kufanywa kwa njia mbalimbali. Unaweza kupanga tofauti kwa kila mwanafunzi. Pia unaweza kufanywa kwa wanafunzi wote, au kikundi kilichochaguliwa.

Njia ya ufautiliaji inategemea madhumuni yake na kikundi cha wanafunzi, kama ifuatavyo:

a) Njia ya Moja kwa Moja (Direct method)

Hii inahusisha mahusiano ya uso kwa uso kati ya wanafunzi wenyewe na kati ya wanafunzi na wakufunzi (mfano: ziara shambani).

b) Njia isiyo ya Moja kwa Moja (Indirect method)

Haisi kuhitaji uso kwa uso.

Inaweza kufanywa kupitia barua, jarida, maswali au kutuma maswali kwa barua kwa majibu.

c) Mchanganyiko wa Njia Zote Mbili

Njia za moja kwa moja zinaamsha motisha zaidi na kutoa msaada, lakini zinahitaji muda mwingi na rasilimali nyingi.

Njia zisizo za moja kwa moja ni gharama ndogo na zinaweza kufikia kikundi kikubwa cha wanafunzi.

Nature and purpose of evaluation

-Concern in evaluation is mostly on determination of the relative values on what is being judged

-Evaluators obtain information to use in making statements of worth value.

-In evaluation –evaluators determine whether the expected or the planned has occurred or is occurring in relation to the intended objectives.

-Evaluation focuses on discovering whether the curriculum is planned, designed, developed and implemented is producing or can produce the desired results.

-The purpose of evaluation in curriculum is to identify- strengths and weaknesses of curriculum before implementation and its effectiveness during and after-SWOT implementation stages of curriculum.

Planning                 Designing                    Develop         Implement         Evaluation

PDf_DIE

-Evaluation enables education evaluators to make decision, draw conclusions and gather data that will support their decision regarding curriculum matters. Sometimes evaluation is for judgment on how well educators communicate with and educate community.

IMPORTANT EVALUATION QUESTIONS

Harrier Talmage has pointed out that a good number of evaluators are desolutioned with evaluation results due to misunderstanding on what evaluation can and cannot do for them. He points out five types of value questions partment to evaluation.

1.QUESTION OF INTRINSIC VALUE (METHODS)

The goodness or appropriateness of the curriculum. The question deals with curriculum as it is planned and with the finished curriculum. It also concerns itself with the appropriateness and goodness of curriculum during delivery.

Eg in a new language curriculum in a school we may ask the following question.

- Does the curriculum incorporate the best thinking on what is known about content of language, assessment of that content and presentation of the content?

- Would specialists in linguistics, composition ,grammer and ponetics give the planned curriculum ‘high marks’ ( contents)

- In this kind of questions people bring in their philosophical and psychological views that is they perceive the curriculum in light of the purpose of education and they see it as paramount and what learning theory they prefer.

- INSTRUMENTAL VALUE

What is good for what? For who? Its benefits? Beneficiaries.

-Evaluators link up the curriculum planned with goals and objectives. They also determined whether what is planned will be attained and to what extend and by which students.

- This question also concerns itself with whether the philosophical and psychological orientation of the curriculum, will be maintained given the suggested content, materials, activities and methods.

- philosophy of the curriculum should the philosophies of the country.

- Philosophical orientation – societal needs eg if the curriculum developer is a humanistic he/she may ask.

- Are the specific objectives stated as planned in the curriculum going to be instrumental in fostering in the students a humanistic orientation towards themselves and others?

-The type of audience to be evaluated must be identified at the beginning because not all cumulative plans may be of value to all students.

3. QUESTION OF COMPARATIVE VALUE

-This kind of question is answered when evaluators are faced with two programmes. Questions:

Is the new programme better than the one it is supposed to replace?

Usually a new programme is created when there is aneed that is when the existing one is inadequate.

-Comparison should not be made on programs that have different goals eg is a programme that which stresses on contemplation of the world better than a programme that stresses skill training?

-The two are different whether one is better than the other relate to the values educators hold about the purpose of education.

-This question is also considered in terms of students achievements eg  of delivery, cost, demand on resources and responsiveness to the expectation of the society.

4.QUESTION OF IDEALIZATION VALUE

Ideal better “fine tune” what we perceive in the mind.

-The concerns of the educators during evaluation are much more than just determining whether what was planned occurred or is occurring they are interested in solidarity data that can help them decide on how to make the programmed the best possible (ideal)

-They also gather information on how the programme is working and looking for alternative ways of making the programme work better in order to optimize students achievement or improve their participation levels in their own learning. Therefore the question requires continuous action throughout delivery of new programme. The education evaluators seek to fine-tune the programmes, contents materials, activities methods, assessment procedures and objectives.

5 Question of decision value.

-Evaluators and curriculum decision makers should have documented evidence that can be used to decide whether to retain, modify or discard complete overhaul) the new programme.

A. ASILI NA MADA YA TATHMINI (Nature and Purpose of Evaluation)

Katika tathmini, shida kuu ni kubaini thamani ya kile kinachochunguzwa.

Wakaguzi hukusanya taarifa ili kutumia katika kutoa maoni ya thamani.

Katika tathmini, wakaguzi huchunguza kama kilichotarajiwa au kilichopangwa kimefanyika au kinaendelea kufanyika kulingana na malengo yaliyokusudiwa.

Tathmini inalenga kubaini kama mtaala uliopangwa, kuundwa, kuendelezwa na kutekelezwa unaleta matokeo yanayotarajiwa au unaweza kuyaleta.

Madhumuni ya tathmini ya mtaala ni kutambua nguvu na udhaifu wa mtaala kabla ya utekelezaji na ufanisi wake wakati na baada ya utekelezaji wa mtaala.

Mchakato wa Mtaala:

Mipango (Planning) → Ubunifu (Designing) → Maendeleo (Develop) → Utekelezaji (Implement) → Tathmini (Evaluation)

PD_DIE

Tathmini inawawezesha wakaguzi wa elimu kufanya maamuzi, kutoa hitimisho, na kukusanya data itakayosaidia maamuzi yao kuhusu masuala ya mtaala.

Wakati mwingine tathmini hufanywa kama hukumu ya jinsi walimu wanavyowasiliana na jamii na kutoa elimu kwa jamii.

MASWALI MUHIMU YA TATHMINI (Important Evaluation Questions)

Harrier Talmage ameonyesha kuwa wakaguzi wengi huchanganyikiwa na matokeo ya tathmini kutokana na kutokuelewa kile tathmini inaweza na haiwezi kufanya. Anaelezea aina tano za maswali ya thamani yanayohusiana na tathmini.

1. SWALI LA THAMANI YA KIASILI (Intrinsic Value / Methods)

Inahusu ubora au unaofaa wa mtaala.

Swali linahusu mtaala kama ulivyopangwa na mtaala uliokamilika. Pia linahusu ufuataji wa mtaala wakati wa utoaji wake.

Mfano: Katika mtaala mpya wa lugha:

a) Je, mtaala unaingiza mawazo bora kuhusu maarifa ya lugha, tathmini ya maarifa hayo, na uwasilishaji wake?

b) Je, wataalamu wa lugha, sarufi, uandishi, na fonetiki wangeipa mtaala alama za juu?

Katika aina hii ya maswali, watu huleta mitazamo yao ya kifalsafa na kisaikolojia, yaani wanauona mtaala kwa mwanga wa malengo ya elimu na nadharia wanayopendelea.

2. THAMANI YA KIFAA (Instrumental Value)

Je, ni vizuri kwa nini? Kwa nani? Manufaa yake? Walengwa?

Wakaguzi wanaunganisha mtaala uliopangwa na malengo na madhumuni, na kubaini kama kilichopangwa kitafanikishwa, na kwa kiasi gani, na na wanafunzi gani.

Swali hili pia linahusiana na msimamo kifalsafa na kisaikolojia wa mtaala, je, utaendelea kulingana na maudhui, vifaa, shughuli na mbinu zilizopendekezwa?

Falsafa ya mtaala inapaswa kuendana na falsafa ya taifa.

Msimamo wa kifalsafa – mahitaji ya jamii. Mfano, kama mtaalamu wa mtaala ni humanist, anaweza kuuliza:

Je, malengo maalumu yaliyowekwa katika mtaala yatachochea wanafunzi kuwa na mtazamo wa kibinadamu kwa wenyewe na wengine?

Hadhira inayotathminiwa lazima itambuliwe mwanzoni kwani si mipango yote itakayokuwa na thamani kwa wanafunzi wote.

3. SWALI LA THAMANI YA KULINGANISHA (Comparative Value)

Huu swali unajibiwa pale wakaguzi wanapokabiliwa na programu mbili.

Swali: Je, programu mpya ni bora kuliko ile inayotarajiwa kubadilishwa?

Mara nyingi, programu mpya inaundwa pale panapohitajika – pale programu ya sasa haiwezi kutimiza mahitaji.

Usipangie kulinganisha programu zenye malengo tofauti, mfano: programu inayolenga kutafakari dunia dhidi ya inayolenga mafunzo ya ujuzi.

Kila programu ina thamani tofauti kulingana na mitazamo ya walimu kuhusu malengo ya elimu.

Swali hili pia linazingatia mafanikio ya wanafunzi, mfano: utoaji wa programu, gharama, mahitaji ya rasilimali, na ulinganifu na matarajio ya jamii.

4. SWALI LA THAMANI YA KIBORA (Idealization Value)

Kibora/ideali kinasaidia "kufinyanga" kile tunachokiona akilini.

Walimu wanapofanya tathmini hawazingatii tu kama kilichopangwa kimefanyika, bali wanatafuta data ya msaada itakayowaongoza kufanya programu kuwa bora zaidi (ideal).

Wanakusanya taarifa jinsi programu inavyofanya kazi na kutafuta njia mbadala za kuboreshwa kwa mafanikio ya wanafunzi au kuimarisha ushirikiano wao katika kujifunza.

Swali hili linahitaji mchakato endelevu wakati wote wa utoaji wa programu mpya.

5. SWALI LA THAMANI YA MAAMUZI (Decision Value)

Wakaguzi na wataalamu wa maamuzi ya mtaala wanapaswa kuwa na ushahidi uliorekodiwa unaoweza kutumika kuamua kudumisha, kubadilisha, au kubatilisha (overhaul) programu mpya.

MEASUREMENT AND EVALUATION.

“ Monitoring and evaluation is a process carried out in a training programme,. Highlight the two types of evaluation and clearly. Compare them in relation to learning/training in a programme.

MEASUREMENT AND EVALUATION

Measurement is the assignment of numerals to events or objects according to certain rules.

-It is a description of a situation or a behavior using numerical terms inorder to avoid value connotation that people can easily associate with words.

-Measurements help us (evaluators) to give values.

-Measurements enables educators to record students degrees of achievement in learning competencies. Once we use the words against the numerals we are already making a value of judgment eg essay writing, marking give marks and remarks.

MONITORING

-This is a type of evaluation that is done when the programme is being implemented with the aim of improving the programme design and functioning while in action.

-It is seen as an internal project activity designed to provide constant feedback on the progress of a programme the problems it is facing and the efficiency with which it is implemented.

Evaluation studies the outcomes of a program eg changes in students performance, benefits to teachers, parents, cost effectiveness etc with the aim of informing the designers of future programmes.

-Evaluation can assess the extent to which the programme intended impact eg better us of learning resources better, teaching methods, gender equity etc.

-It can also evaluate cost – effectiveness of the programme as compared to other options eg increase in book ration and increase of teachers which is more cost-effective having the same results.

-There is the need to point out which areas need monitoring and which ones need evaluation right at the design stage of a programme.

MandE systems can be effective way to

- Provide constant feedback on the extent to which the programmes are achieving their goals.

- Identify potential problems at an early stage and propose possible solutions.

- Monitor the accessibility of the programme to all sectors of target population.

- Monitor the efficiency with which the different components of the programme are being implemented and suggest improvements.

- Evaluate the extent to which the programme is able to achieve its general objectives.

- Cost effectiveness of the programme

- Re-organize different aspects of the programmes whether to terminate or adopt.

- Justify the continuity of the programme.

- Informed decision-making

- Justify for further funding

.Provide guidelines for designing future programme.

- For comparison with other similar programme.

- Identify the time taken

- Incorporate the views of stakeholders.

- Awareness is growing that participation by programme beneficiaries in design  and implementation brings greater ownership of programme objectives and encourages sustainability of programmes benefits ownership brings accountability

TYPES OF EVALUATION………….ISFD

- Diagnostic evaluation

- Formative evaluation

- Summative evaluation

- Impact evaluation

DIAGNOSTIC EVALUATION

-Some authors delineate the diagnostic evaluation as a component of formative evaluation. However some others consider it as a distinct form of measurement.

- Diagnostic assessment provides instructions with information about students prior knowledge and misconception before the beginning of a learning action.

-They also provide a baseline for understanding how much learning has taken place after the learning activity is computed.

- Instructors usually build concepts sequencially through out the course eg in sentence formation simple sentences will be taught before compound sentences.

-Diagnostic assessment given is after simple but before compound sentences will provide opportunities to determine if the students remember the concept they need if some students do not then refresher will make the compound sentence activity more meaningful.

-Therefore diagonistic assessment permits the instructor to remediate students and adjust the curriculum to meet each pupils unique needs.

SOURCES OF DIAGNOSTIC ASSESSMENT

- Summative assessment of previous evaluation

- Document analyses/observation

- Short assessment that focus on key knowledge and concepts (CATS)

- A. UPIMAJI NA TATHMINI (Measurement and Evaluation)

- “Ufuatiliaji na tathmini ni mchakato unaofanywa katika programu ya mafunzo.”

- Taja aina mbili za tathmini na zingatie tofauti zao kwa uwazi. Linganisha kwa muktadha wa kujifunza/mafunzo katika programu.

- UPIMAJI (Measurement)

- Upimaji ni ugawaji wa nambari kwa matukio au vitu kulingana na kanuni fulani.

- Ni maelezo ya hali au tabia kwa kutumia maneno ya nambari ili kuepuka tafsiri za thamani ambazo watu wanaweza kuhusisha kwa urahisi na maneno.

- Vipimo husaidia wakaguzi kutoa thamani za matokeo.

- Vipimo vinawezesha walimu kurekodi kiwango cha ufanisi wa wanafunzi katika ujuzi wa kujifunza.

- Mara tunapotumia maneno dhidi ya nambari, tayari tunatoa hukumu ya thamani, mfano: uandishi wa insha, alama na maoni.

- UFUATILIAJI (Monitoring)

- Hii ni aina ya tathmini inayofanywa wakati programu inaendeshwa, kwa lengo la kuboresha muundo na utendaji wa programu wakati inaendelea.

- Inaonekana kama shughuli ya ndani ya mradi inayolenga kutoa maoni ya mara kwa mara juu ya maendeleo ya programu, matatizo yanayokabiliwa, na ufanisi wake.

- TATHMINI (Evaluation)

- Tathmini inasoma matokeo ya programu, mfano: mabadiliko katika utendaji wa wanafunzi, manufaa kwa walimu, wazazi, gharama, ufanisi wa rasilimali, n.k., kwa lengo la kuarifu waandaaji wa programu za siku za usoni.

- Tathmini inaweza kubaini kipimo ambacho programu inafanikisha malengo yake, mfano: matumizi bora ya rasilimali za kujifunzia, mbinu bora za kufundisha, usawa wa kijinsia, n.k.

- Pia inaweza kutathmini ufanisi wa gharama ikilinganisha na chaguzi nyingine. Mfano: ongezeko la vitabu vs ongezeko la walimu – ni ipi bora kwa gharama chini ya matokeo sawa.

- Ni muhimu kubaini sehemu gani zinahitaji ufuatiliaji na sehemu gani tathmini tayari katika hatua ya muundo wa programu.

- MIFANO YA HUDUMA YA MONITORING NA EVALUATION (MandE)

- Kutoa maoni ya mara kwa mara juu ya kufanikishwa kwa malengo ya programu.

- Kutambua matatizo mapema na kupendekeza suluhisho.

- Kufuatilia upatikanaji wa programu kwa sekta zote za walengwa.

- Kufuatilia ufanisi wa vipengele tofauti vya programu na kupendekeza maboresho.

- Kutathmini kiwango ambacho programu inaweza kufanikisha malengo yake ya jumla.

- Ufanisi wa gharama wa programu.

- Kuratibu vipengele tofauti vya programu – kuendelea au kusitisha.

- Kuthibitisha kuendelea kwa programu.

- Kufanya maamuzi yaliyo sahihi.

- Kutaka ufadhili zaidi.

- Kutoa miongozo kwa muundo wa programu za siku za usoni.

- Kulinganisha na programu nyingine zinazofanana.

- Kubaini muda unaohitajika.

- Kujumuisha maoni ya wadau.

- Uelewa unakua kuwa ushiriki wa walengwa katika muundo na utekelezaji huongeza umiliki wa malengo ya programu na kuhimiza uhifadhi wa manufaa ya programu.

- AINA ZA TATHMINI (Types of Evaluation) – ISFD

- Tathmini ya Uchunguzi (Diagnostic Evaluation)

- Tathmini ya Kimuundo (Formative Evaluation)

- Tathmini ya Mwisho (Summative Evaluation)

- Tathmini ya Athari (Impact Evaluation)

- TATHMINI YA UCHUNGUZI (Diagnostic Evaluation)

- Waandishi wengine wanaona tathmini ya uchunguzi kama sehemu ya tathmini ya kimuundo, lakini wengine wanaiona kama aina tofauti ya upimaji.

- Tathmini ya uchunguzi hutoa taarifa juu ya maarifa na dhana zisizo sahihi za wanafunzi kabla ya kuanza kwa mchakato wa kujifunza.

- Pia hutoa msingi wa kuelewa kiasi gani cha kujifunza kimefanyika baada ya shughuli ya kujifunza.

- Wakufunzi hutoa maana kwa mtiririko katika kozi, mfano: katika uundaji wa sentensi, sentensi rahisi hufundishwa kabla ya sentensi changamano.

- Tathmini ya uchunguzi inatoa fursa ya kurekebisha wanafunzi na kubadilisha mtaala ili kukidhi mahitaji ya kila mwanafunzi.

- VYANZO VYA TATHMINI YA UCHUNGUZI

- Tathmini ya mwishoni ya tathmini zilizopita.

- Uchambuzi wa nyaraka / uchunguzi.

- Tathmini fupi inayolenga maarifa na dhana muhimu (CATS).

FORMATIVE

-Formative is done when the programme is still ongoing ‘fluid’. When activities are forming

-they help in examining the delivery of a programme or a technology. The quality of its implementation and the assessment of the organizational context, personnel procedures, inputs etc.

Its characteristics

-done when the programme is being implemented or as activities are progressing.

- It monitors progress towards the achievement of the set targets.

-Evaluators are the people implementing the activities.
-done after short intervals eg daily,weekly.

-It assesses each activity separately.

The objectives are specific.

Examples of formative

- Need assessment which determines the gap who needs the programme how great the need is what might work to meet the need.

- Evaluability assessment- it determines whether an evaluation is feasible and whose stakeholders can check its usefulness.

- Structural conceptualization which helps stakeholders define the programme or technology, the target population and the possible outcome.

- Implementation evaluation – investigates the process delivering the programme or technology including alternative procedures.

FORMATIVE QUESTIONS.

- What is the definition and the scope of the problem or issue at hand?

- Methods used to identify FGD, Q/A, Stakeholder analysis input/output analysis, nominal, group techniques etc.

- Where is the problem and how serious it is need assessment through interviews, document analysis, FGD, Survey, expert testimony etc.

- Where is the problem and how serious is it? Need assessment through interviews, document analysis, FGD, survey, expert testimony etc.

- How should the programme be delivered/implemented to address the problem?

Methods used

- Stakeholders analysis, case study/comparative study, decision making methods, participatory methods.

- How well is the programme delivered?

Methods used

Implementation assessment methods, monitoring techniques, management information systems.

SUMMATIVE EVALUATION

-They examine the effects or outcomes of a programme. They summarize it by describing what happens after the delivery of a programme can be said to have caused the outcome determining the overall impact of the causal factors beyond the immediate target outcome and estimating the relative cost and benefits associated with the programme input and output outcomes impact.eg

FPE/FDSE (KESSP)

Programme: school instructional materials

Inputs                   Outputs                                    outcomes                         impact

Textbooks             improved ratio                        improved                         reduced

Ref books              better learning                        performance                    poverty

Writing materials                                                                                          level

ITS CHARACTERISTICS

-Done at the end of the programme

-it covers all activities

-Evaluators are not part of the implementation team

-it is outcome oriented. It finds out whether objectives have been achieved.

-The objectives are general.

-It takes place after a long time.

TYPES OF SUMMATIVE

1 Outcome evaluation – caused demonstrable effects –specifically defined target outcomes.

2. Cost effectiveness and cost benefit analysis efficiency values/standardized outcomes cost and value monitoring.

3. Secondary analysis – re-examines existing data.

- used to address new questions that may come up.

-uses methods that were not previously employed alternative methods.

4 Meta-analysis

-integrates the outcome estimates from the multiple studies carried out to arrive at an overall or summary judgement greater extend.

5. Impact evaluation – broader

-Assess the overall or net effects whether intended or unintended.

SUMMATIVE QUESTIONS

1.What type of evaluation is feasible?

Methods used.

-evaluation assessment

2. What was the effectiveness of the programme?

Methods/techniques.

Survey, observation, correlational methods, quasi, experimental etc.

3. What is the impact of the programme?

Techniques used.

Observation, econometric methods etc.

A. TATHMINI YA KIMUUNDO (Formative Evaluation)

Formative hufanywa wakati programu bado inaendelea (inaendelea kubadilika).

Inasaidia kuchunguza utoaji wa programu au teknolojia, ubora wa utekelezaji wake, na tathmini ya muktadha wa shirika, taratibu za wafanyakazi, rasilimali na nyinginezo.

Sifa zake

Hufanywa wakati programu inaendelea au shughuli zinaendelea.

Inafuatilia maendeleo kuelekea kutimiza malengo yaliyowekwa.

Wakaguzi ni watu wanaotekeleza shughuli.

Hufanywa baada ya vipindi vifupi, mfano kila siku au kila wiki.

Inapima kila shughuli kila moja kwa moja.

Malengo yake ni maalumu.

Mifano ya formative evaluation

Tathmini ya mahitaji (Need Assessment) – kubaini pengo, nani anayehitaji programu, ukubwa wa hitaji, na ni nini kingefaa kutimiza hitaji.

Tathmini ya Uwezekano (Evaluability Assessment) – kubaini kama tathmini inaweza kufanyika na wadau gani wanaweza kuangalia manufaa yake.

Ufafanuzi wa Muundo (Structural Conceptualization) – husaidia wadau kufafanua programu/teknolojia, idadi ya walengwa, na matokeo yanayoweza kutokea.

Tathmini ya Utekelezaji (Implementation Evaluation) – kuchunguza mchakato wa utoaji wa programu/teknolojia ikiwa ni pamoja na mbinu mbadala.

Maswali ya Formative

Nini ufafanuzi na wigo wa tatizo?

Mbinu: FGD, maswali/jibu (Q&A), uchambuzi wa wadau, uchambuzi wa input/output, mbinu za kikundi.

Tatizo liko wapi na ni kubwa kiasi gani?

Tathmini ya mahitaji: mahojiano, uchambuzi wa nyaraka, FGD, tafiti, ushuhuda wa wataalamu.

Je, programu inafanywaje ili kushughulikia tatizo?

Mbinu: uchambuzi wa wadau, masomo ya kesi, ulinganifu, mbinu za maamuzi, mbinu za ushiriki.

Je, programu inatolewa vizuri kiasi gani?

Mbinu: tathmini ya utekelezaji, mbinu za ufuatiliaji, mifumo ya taarifa ya usimamizi.

TATHMINI YA MWISHO (Summative Evaluation)

Huchunguza athari au matokeo ya programu.

Inasummary kwa kuelezea kinachotokea baada ya utekelezaji na kubaini ni vipengele gani vilichangia matokeo.

Inakadiria gharama na manufaa yanayohusiana na rasilimali na matokeo ya programu.

Mfano: FPE/FDSE (KESSP) – Programu: vifaa vya kufundishia shule

Inputs	Outputs	Outcomes	Impact

Vitabu vya shule	Uwiano ulioboreshwa	Utendaji ulioboreshwa	Kupunguza umasikini

Vitabu vya marejeo	Mafunzo bora	Utendaji ulioboreshwa

Vifaa vya uandishi

Sifa zake

Hufanywa mwisho wa programu.

Inashughulikia shughuli zote.

Wakaguzi si sehemu ya timu ya utekelezaji.

Inalenga matokeo.

Inabaini kama malengo yamefikiwa.

Malengo yake ni ya jumla.

Hufanywa baada ya muda mrefu.

Aina za Summative Evaluation

Tathmini ya matokeo (Outcome Evaluation) – inaonyesha matokeo yanayoweza kuonekana.

Tathmini ya gharama na manufaa (Cost Effectiveness / Cost-Benefit Analysis) – kuangalia ufanisi wa gharama, thamani, viwango vya matokeo.

Uchambuzi wa pili (Secondary Analysis) – kuangalia data iliyopo tena kwa ajili ya maswali mapya.

Meta-analysis – kuunganisha makadirio ya matokeo kutoka tafiti nyingi ili kupata hukumu ya jumla.

Tathmini ya Athari (Impact Evaluation) – kupima athari jumla, zikusudiwa au zisizokusudiwa.

Maswali ya Summative

Ni aina gani ya tathmini inawezekana?

Mbinu: tathmini ya jumla.

Je, programu ilikuwa na ufanisi gani?

Mbinu/mbinu: tafiti, uchunguzi, ulinganifu, majaribio, nk.

Je, athari ya programu ni ipi?

Mbinu: uchunguzi, mbinu za kiuchumi (econometric methods), nk.

A

IMPACT EVALUATION

-Impact evaluation is an evaluation carried out sometimes (3-10 yrs) after intervention has been completed so as to allow time for impact to appear.

-It is also an evaluation which looks at the impact of an intervention on final outcome rather than at project outcome or process evaluation which focuses on implementation.

-World bank independent evaluation group (IE) is the systematic identification of the effective positive or negative, intended or not on individual, households institutions and the environment caused by a given development activity such as a programme or a project.

. Impact evaluation seeks to answer cause and effect questions. It helps to answer key questions for evidence based policy making eg what works, what doesn’t why and for how much.

- IFAD impact evaluation defines impact as the attainment of development of goals of the project/programme.

-impact evaluation establishes whether the intervention had a welfare effects on individuals, households and communities and whether this intervention can be attributed to the concerned interventions.

-Impact evaluation assesses the changes that can be attributed to a particular intervention such as project, program or policy both the intended ones as well as ideally the intended ones.

-In contact to outcome monitoring which examines whether the target has been achieved.

-Impact evaluation is structured to answer the question how would outcome such as particular wellbeing have changed if the intervention had not been under taken

-It assesses the positive and negative primary and secondary, long term effects produced by development whether directly or indirectly intended or unintended.

-international initiative for impact evaluation defines i.e as an analysis that measure the net changes in outcomes that can be attributed to a specific programme using the best methodology available feasible and appropriate to the evaluation question that is being investigated and to a specific context.

ASSIGNMENT

What impact does evaluation of learning has on

- Test construction

- Types of tests

- Marking and grading of students.

(According to your interpretation)

WHEN DO WE CONDUCT IMPACT EVALUATION

It is not feasible to conduct impact evaluation for all interventions. There is need to build a strong evidence based on all sectors in a variety of context so as to provide guidance for policy makers.

- The types of interventions that would call for an impact evaluation include:

i) Innovative programmes or projects (new)

ii) Pilot programmes which are due to be scaled up.

iii) Interventions in which there is scarcity solid evidence of impact in the given context.

IMPACT EVALUATION DESIGN

-They are identified by the type and method used to generate the counter factual verses without. This classification are done in three types;

1 Experimental

2 Quasi – experimental

3 non-experimental

COMPONENTS OF MONITORING

1) Technical performance – quality of a programme or project.

2) Scheduled performance – checks whether activities were completed on time.

3) Cost performance – checks whether cost of completing each activity was what was budgeted for.

HOW TO CONDUCT PROJECT MONITORING

- Gather information –gathered during the implementation.

- Status of activities – monitoring team compare the status of activities and activity plan.

- Establishes causes of deviations.

- If there are differences between, what are the reasons behind?

- Take action – may be re-planning and re-scheduling or adding more resources in terms of people, money or materials to meet the set goals /deadlines.

B

TATHMINI YA ATHARI (IMPACT EVALUATION)**

Tathmini ya athari ni aina ya tathmini inayofanywa baada ya muda (miaka 3–10) tangu uingiliaji kati kukamilika ili kuruhusu athari kuonekana.

Pia ni tathmini inayochunguza athari za uingiliaji kwenye matokeo ya mwisho, badala ya matokeo ya mradi au tathmini ya mchakato ambayo hulenga utekelezaji.

Benki ya Dunia – Kitengo Huru cha Tathmini (IEG) hufafanua tathmini ya athari kama utambuzi wa kimfumo wa athari chanya au hasi, zilizokusudiwa au zisizokusudiwa kwa watu binafsi, kaya, taasisi na mazingira zinazosababishwa na shughuli fulani ya maendeleo kama programu au mradi.

Impact evaluation hutafuta kujibu maswali ya kisababisho (cause and effect). Husaidia kutoa majibu muhimu kwa utungaji sera unaoegemea ushahidi, mfano: nini kinafanya kazi? Kipi hakifanyi kazi? Kwa nini? Na kwa gharama gani?

IFAD hufafanua impact evaluation kama kufikiwa kwa malengo ya maendeleo ya mradi/programu.

Tathmini ya athari huonyesha kama uingiliaji ulisababisha mabadiliko ya ustawi kwa watu binafsi, kaya au jamii, na kama mabadiliko hayo yanaweza kuhusishwa moja kwa moja na uingiliaji huo.

Inapima mabadiliko yanayotokana na uingiliaji fulani (mradi, programu au sera) – yaliokusudiwa na yasiyokusudiwa.

Kinyume na outcome monitoring inayotazama tu kama malengo yamefikiwa, impact evaluation huuliza:

“Matokeo yangekuwaje kama uingiliaji usingefanyika?”

Inapima athari chanya na hasi, za msingi na za sekondari, za muda mrefu, za moja kwa moja au zisizo za moja kwa moja.

Shirika la International Initiative for Impact Evaluation (3ie) hufafanua impact evaluation kama uchambuzi unaopima mabadiliko halisi (net change) yanayoweza kuhusishwa moja kwa moja na programu fulani, kwa kutumia mbinu bora na zinazofaa kwa swali la tathmini na muktadha husika.

ASSIGNMENT (Kazi ya nyumbani)

Athari gani tathmini ya ujifunzaji ina kwa:

a) Uundaji wa mitihani

b) Aina za mitihani

c) Uwekaji alama na upangaji madaraja ya wanafunzi

(Kulingana na uelewa wako)

WAKATI WA KUFANYA TATHMINI YA ATHARI

Si vyema kufanya impact evaluation kwa kila uingiliaji. Kuna haja ya kujenga ushahidi madhubuti katika sekta mbalimbali ili kuwasaidia watunga sera.

Aina za uingiliaji zinazohitaji impact evaluation ni pamoja na:

i) Miradi au programu za ubunifu (innovative)

ii) Programu za majaribio (pilot programmes) zinazotarajiwa kupanuliwa

iii) Uingiliaji ambao hakuna ushahidi wa kutosha kuhusu athari zake katika muktadha husika

UBUNIFU WA TATHMINI YA ATHARI (IMPACT EVALUATION DESIGN)

Hutofautishwa kulingana na mbinu za kuzalisha counterfactual (hali bila programu). Aina tatu kuu ni:

Experimental (Majaribio)

Quasi-experimental

Non-experimental

VIPENGELE VYA UFUATILIAJI (MONITORING COMPONENTS)

Utendaji wa kiufundi – ubora wa programu au mradi.

Utendaji wa ratiba (Scheduled performance) – kama shughuli zimekamilishwa kwa wakati.

Utendaji wa gharama (Cost performance) – kama gharama zinazoonekana zinawiana na bajeti ya kila shughuli.

JINSI YA KUFANYA UFUATILIAJI WA MRADI (PROJECT MONITORING)

Kukusanya taarifa – wakati wa utekelezaji.

Hali ya shughuli – timu ya ufuatiliaji inalinganisha hali halisi ya utekelezaji na mpango wa shughuli.

Kubaini sababu za tofauti – sababu za kutofautiana kati ya mpango na utekelezaji.

Kuchukua hatua – inaweza kuwa kupanga upya, kuratibu upya, au kuongeza rasilimali (watu, fedha, vifaa) ili kufikia malengo yaliyowekwa.

A

PROJECT MONITORING INDICATORS

- Indicators are factors or sings which shows the status of project activities at a specified time.

- Useful in comparing the actual and expected results.

- Allows managers or implementers to compare project inputs with project output.

TYPES OF MONITORING INDICATORS

1) Operational indicators – measure the input, the process and the output of a project.

a)Input – resources required by different project activities. They are inform of people, materials and finances monitories ensures resourcesare ordered, received and given out on time. Ensure resources are well utilized.

b)Process – are operations about how inputs are combined to produce output.

-Ensures that work is progressing according to plan. Also checks work standards.

-measures the extent to which activities are progressing.

c) Output – Services offered.

-Monitoring ensures that product and services are of quality.

-output indicators measure the extent to which output have been produced.

- Performance indicators

Signs that show the effects and the impact of a project.

- Effect – short term outcome of an activity or project.

- Measure the extent to which the specific objectives have been achieved.

- Impact – long term outcome of an activity or project.

- Measure the extent to which the general objectives or goals of the project have been achieved.

- Shows whether the project has made a positive impact by comparing the situation before the implementation of the project and after implementation eg HIV/AIDS and water borne diseases.

MONITORING TOOLS

1) Progress reports – may be kept daily, weekly, monthly quarterly and annually.

- will have objectives achieved, work done and the degree to which each work has been done.

-They are kept by project implementers, project monitoring team,analyses the project report.

2. Meetings – monitoring team holds meetings with implementers or beneficiaries of the project

3. Field visits.

-may be done daily, weekly, monthly etc.

-Provides quantitative and QL data. The monitoring team will observe and interview the beneficiaries, community or other groups in the programme.

4. Tracking of inputs

-will show resources delivered, what has been used and what is remaining. The monitoring team will check whether resources may be over/under utilized.

- Checklists/questionnaires/inquiry forms.

APPROACHES TO M/E

Essentially M and E is about gathering data and combining data in relation to weighted set of goals or scales in order to allow people to make judgment about value.

-Educators must consider whether the results to obtain are worthy the cost to be incurred in delivering them. The way data is processed is influenced by philosophical and psychological perspectives of the evaluators.

BEHAVIOURISTS APPROACH.

-Prefer a sequenced approach, they spell out specific entitites of curriculum eg they would have clearly stated objectives so that they can an act procedures that will varnish with precise indicators of the achievement of the intended outcomes of the programme.

eg FPE Objective: to improve pupils performance and increase retention through improved provision of instructional materials.

-One of the indicators was increase by june 2006. In proportion of children reaching desired standards of achievement in English, mathematics, science and Kiswahili in std 2, 4, 6 disaggregated by gender, county rural, urban and intra rural.

- Whatever the perspective, evaluators recognize evaluation involving a managerial and a decision making dimension.

1. Plan how they will obtain data (evaluation plan) be clear where to start

2. Should be able to communicate to students and others on the effectiveness of the curriculum using different methods feedback mechanism eg through workshops, pamphlets etc.

3. Should be able to understand how to manage themselves, evaluation actions and manage others involved in evaluation.

4. Be able to determine criteria to employ to judge some aspects of the programme

-Lee Crombach has specified three types of decision for which evaluation could be used.

1. Decision about course improvement. Evaluators would like to a certain what effects (the course has/had on the learners and compare the effects attained with the intended effects.

2. Decision about individuals, teachers and students

-Evaluators will vanish data that will help them understand what in the course is producing the effects and what parameters influence its effectiveness.

Eg evaluation may discover that teachers attitudes is influencing learners achievement in that course.

- Decision about administrative regulations. How good is the educational system.

B

A. VIASHIRIA VYA UFUATILIAJI WA MRADI (PROJECT MONITORING INDICATORS)

Viashiria ni mambo au ishara zinazoonyesha hali ya shughuli za mradi katika kipindi fulani.

Husaidia kulinganisha matokeo halisi na yale yaliyotarajiwa.

Huwawezesha wasimamizi au watekelezaji kulinganisha pembejeo za mradi na matokeo yake.

AINA ZA VIASHIRIA VYA UFUATILIAJI

1) Viashiria vya Uendeshaji (Operational Indicators)

Hupima pembejeo (inputs), michakato (processes), na matokeo (outputs) ya mradi.

a) Pembejeo (Input)

Hizi ni rasilimali zinazohitajika kutekeleza shughuli mbalimbali za mradi, kama watu, vifaa, na fedha.

Ufuatiliaji huhakikisha rasilimali zinaagizwa, kupokelewa na kutolewa kwa wakati.

Pia huhakikisha rasilimali zinatumika ipasavyo.

b) Mchakato (Process)

Ni hatua au shughuli zinazoonyesha jinsi pembejeo zinavyounganishwa ili kutoa matokeo.

Ufuatiliaji huhakikisha kazi inaendelea kulingana na mpango na viwango vinazingatiwa.

Hupima kiwango ambacho shughuli zinaendelea.

c) Matokeo (Output)

Ni huduma au bidhaa zinazotolewa na mradi.

Ufuatiliaji huhakikisha bidhaa na huduma ni za ubora.

Viashiria hivi hupima kiwango ambacho matokeo yametolewa.

2) Viashiria vya Utendaji (Performance Indicators)

Ni ishara zinazoonyesha athari na madhara ya mradi.

a) Athari (Effect)

Matokeo ya muda mfupi ya shughuli au mradi.

Hupima kiwango ambacho malengo mahususi yamefikiwa.

b) Madhara/Matokeo ya muda mrefu (Impact)

Matokeo ya muda mrefu ya mradi.

Hupima kiwango ambacho malengo ya jumla yamefikiwa.

Huonyesha kama mradi umeleta manufaa kwa kulinganisha hali kabla na baada ya utekelezaji, mfano katika kupunguza VVU/UKIMWI au magonjwa yatokanayo na maji machafu.

VYOMBO VYA UFUATILIAJI (MONITORING TOOLS)

Taarifa za maendeleo (Progress reports)

Huandikwa kila siku, wiki, mwezi, robo mwaka au mwaka.

Huonyesha malengo yaliyofikiwa, kazi iliyofanyika na kiwango cha utekelezaji.

Huandaliwa na watekelezaji wa mradi na kuchambuliwa na timu ya ufuatiliaji.

Mikutano

Timu ya ufuatiliaji hufanya mikutano na watekelezaji au wanufaika wa mradi.

Ziara za mashambani (Field visits)

Hufanyika kila siku, wiki, mwezi n.k.

Hutumika kukusanya data ya kiasi (quantitative) na ubora (qualitative).

Timu ya ufuatiliaji huhoji na kuangalia wanufaika, jamii au makundi mengine yanayohusika.

Ufuatiliaji wa pembejeo (Tracking of inputs)

Huonyesha rasilimali zilizowasilishwa, zilizotumika, na zilizobaki.

Husaidia kubaini kama rasilimali zinatumika kupita kiasi au chini ya kiwango.

Orodha za ukaguzi, dodoso na fomu za uchunguzi

MBINU ZA UFUATILIAJI NA TATHMINI (APPROACHES TO M/E)

Ufuatiliaji na tathmini kwa ujumla ni ukusanyaji wa data na kuichanganya kulingana na malengo yaliyopangwa ili kuruhusu watu kutoa hukumu juu ya thamani ya mradi.

Walimu na wasimamizi wanapaswa kuzingatia kama matokeo wanayotaka kupata yanastahili gharama zinazotumika kuyafikia.

Namna data inavyosindikwa huathiriwa na mitazamo ya kifalsafa na kisaikolojia ya mthamini.

MBINU YA TABIA (BEHAVIOURIST APPROACH)

Wanapendelea mbinu ya mfuatano, ambapo malengo ya mtaala yanatajwa wazi ili kuwezesha utekelezaji wa taratibu zenye viashiria vya moja kwa moja vya mafanikio.

Mfano: Lengo la FPE ni kuboresha ufaulu na kuongeza kudumu kwa wanafunzi kupitia utoaji bora wa vifaa vya kufundishia.

Mfano wa kiashiria (2006):

Kuongezeka kwa watoto wanaofikia viwango vinavyohitajika katika masomo ya Kiingereza, Hisabati, Sayansi na Kiswahili kwa darasa la 2, 4 na 6 kwa kuzingatia jinsia, kaunti, maeneo ya vijijini na mijini.

Waathmini hutambua kuwa tathmini inahusisha vipengele vya usimamizi na utoaji wa maamuzi:

Kupanga jinsi ya kukusanya data (mpango wa tathmini) na kubainisha pa kuanzia.

Kuwasiliana na wanafunzi na wadau wengine kuhusu ufanisi wa mtaala kupitia mbinu mbalimbali za mrejesho kama warsha na vijitabu.

Kujisimamia na kusimamia wengine wanaohusika katika tathmini.

Kuweka vigezo vya kupima baadhi ya vipengele vya programu.

Lee Cronbach alibainisha aina tatu za maamuzi muhimu katika tathmini:

Maamuzi kuhusu kuboresha kozi

Mthamini hutaka kujua athari za kozi kwa wanafunzi na kulinganisha matokeo na malengo yaliyokusudiwa.

Maamuzi kuhusu watu binafsi – walimu na wanafunzi

Tathmini hutoa data inayoonyesha mambo yanayoathiri mafanikio ya kozi.

Mfano: Tathmini inaweza kubaini kuwa mtazamo wa mwalimu unaathiri ufaulu wa wanafunzi.

Maamuzi kuhusu kanuni na usimamizi (administrative regulations)

Huuliza: Je, mfumo wa elimu unafanya vizuri?

A

SPECIFIC APPROACHES

1Scientific and humanistic approaches

- Lee Crowback presents two basic approaches as opposite extremes. He advocates the scientific approach prize experiment whereas the proponent of the humanistic approach feel that experimental are mis- informative.

SCIENTIFIC APPROACH

-The scientific ideal person is a believer in true experiment. They concentrate their efforts on change in learners behavaior.

-Data is presented mostly in form of test scores. They compare students achievement in different situations each controlled as much as is feasible. Information collected is quantified so that it is analyzable scientifically. Decisions on the programmes are made on the basis of the comparative information gained through evaluation efforts.

HUMANISTIC APPROACH

-Data gathered is qualitative in nature. The evaluator relies more on impressions of what is observed.

- In reporting, he engages in ‘thick’ descriptions of actual incidences. Data gained through interview discussion and patterns made during observations form part of the data analyses. (categorizes themes)

Sub-theme trends

-Very few evaluators will follow one approach in total. A friend of between the two is usually made, whatever the approach the common thesis of evaluation is maintained (decision making).

2. Intrinsic and pay off approach.

-Evaluators either study curriculum plan separately or study the effects of Curriculum after it has been implemented.

-Shriven calls the former type of intrinsic evaluation and the latter pay-off evaluation.

- In the intrinsic type of evaluation the criteria of evaluation is usually operationally formulated.

-Evaluator answer the question. How good is the curriculum?

-The criteria employed refer to the curriculum itself, operationalize – translate into a form of measurable eg intelligence (IQ) What shall we study?

-Evaluators study the content, they look in to the way the content is organized and sequenced, the appropriateness of the content the strategies of passing the content, materials selected, skills required etc.

-The evaluators may assume that if a curriculum has a sound plan then it will be effective in stimulating particular student learning.

PAY OFF EVALUATION.

-After establishing the worth of a curriculum after delivery it is equally important to evaluate its effectiveness after implementation.Shrivencalls this pay-off evaluation the outcomes are usually operationally defined.

-Evaluators considers the effects of the curriculum on learners, teachers, administrators and even parents.

- This approach may involve making judgments regarding the differences between pre-test and post-test and experimental groups and control groups.

-The proponents of this type of evaluation says that this is the best type of evaluation for it shows the effects of the curriculum on the learner.

- 3. Formative and summative.

- Formative evaluation encompasses those activities undertaken to improve an existing programme.

- Evidence is sort on how to support decisions made on revisions of a programme while it is being developed (data collected during the developmental stage of the programme in order to improve it before it is implemented country wide.

-During developmental and early piloting stages evaluation activities provide frequent and detailed data to guide developers in their action. Formative education takes place at a number of specified points during curriculum development process eg during curriculum creation evaluators can check the validity of the content and make modification.

-The purpose of formative evaluation is to guide creation and to fine tune curriculum. It allows teachers and others involved in the evalution to determine whether the intended is occurring and also to record and examine the presence of unintended effects.

-Formative evaluation uses the process of feedback and adjustment there by keeping the curriculum development process “ open”

summative evaluation.

-aims at getting the total picture of the quality of the produced curriculum.

-It is usually undertaken after the curriculum has been implemented countrywide.

-The focus is on the effectiveness of the total curriculum. The major purpose is to allow the involved parties to draw conclusions about how well the curriculum has worked

- S.E obtains evidence of the summed effects of the various components or sub-components of a particular curriculum.

- A comprehensive summative evaluation can be planned for certain strategic end points during curriculum development process eg at the end of piloting, before final implementation stage. This allows the evaluators to have a total fiction of evolving curriculum product.

1. Design- develop other sub components-pilot – implement –evaluate

-while formative evaluation may use informal method of data collection.

-summative evaluation uses formal method of data collection instruments are well designed, test for measuring attainments of objectives carefully designed and analysis procedures carefully set out.

B

A. MBINU MAALUM (SPECIFIC APPROACHES)

1. Mbinu za Kisayansi na Kibinadamu (Scientific and Humanistic Approaches)

Lee Cronbach anaonyesha mbinu mbili za msingi kama zilizo kinyume. Anaunga mkono mbinu ya kisayansi inayothamini majaribio, ilhali wafuasi wa mbinu ya kibinadamu wanahisi kuwa majaribio yanaweza kutoa taarifa zisizo kamili.

MBINU YA KISAYANSI (SCIENTIFIC APPROACH)

Mthamini wa kisayansi ni mtu anayeamini majaribio ya kweli (true experiments).

Huangazia zaidi mabadiliko katika tabia za wanafunzi.

Data huwasilishwa kwa mfumo wa alama za mitihani.

Wanalinganisha ufaulu wa wanafunzi katika mazingira tofauti ambayo yamedhibitiwa kadiri iwezekanavyo.

Taarifa inayokusanywa hupangwa kwa namba ili iweze kuchambuliwa kisayansi.

Maamuzi kuhusu programu hufanywa kulingana na taarifa za kulinganisha zilizopatikana kupitia tathmini.

MBINU YA KIBINADAMU (HUMANISTIC APPROACH)

Data inayokusanywa huwa ya aina ya ubora (qualitative).

Mthamini hutegemea zaidi taswira za kile alichokiona au kukishuhudia.

Katika kuripoti, hutumia maelezo marefu (thick descriptions) ya matukio halisi.

Data kutoka kwa mahojiano, majadiliano, na mifumo iliyobainishwa wakati wa uchunguzi huwa sehemu ya uchambuzi wa data.

Mada ndogo na mwenendo hutambuliwa na kuainishwa.

Kidokezo: Ni wachache sana wanaofuata mbinu moja tupu — wengi hutumia mchanganyiko wa mbinu hizi mbili. Iwe ni mbinu gani, lengo kuu la tathmini hubaki kutoa msingi wa kufanya maamuzi.

2. Mbinu ya Ndani (Intrinsic) na Matokeo (Pay-off Approach)

Wathamini wanaweza kusoma mpango wa mtaala kabla ya utekelezaji wake au kuchunguza matokeo yake baada ya kutekelezwa.

Shriven anaita tathmini ya kwanza (kupima mpango kabla ya kutekelezwa) intrinsic evaluation na tathmini ya pili (kupima baada ya utekelezaji) pay-off evaluation.

TATHMINI YA NDANI (INTRINSIC EVALUATION)

Vigezo vya tathmini hutolewa kwa njia ya kiutendaji (operationally formulated).

Mthamini huuliza: “Je, mtaala huu ni mzuri kiasi gani?”

Vigezo vinavyotumika vinahusu mtaala wenyewe, mfano kuutafsiri katika hali inayoweza kupimika kama IQ.

Mthamini huchunguza:

Mfuatano wa maudhui

Ulinganifu wa maudhui

Mbinu za ufundishaji zinazopendekezwa

Vifaa vyote vinavyohitajika

Ustadi unaotarajiwa

Mthamini anaweza kudhani kuwa kama mtaala una mpango mzuri basi utakuwa na ufanisi katika kuchochea ujifunzaji mahususi wa wanafunzi.

TATHMINI YA MATOKEO (PAY-OFF EVALUATION)

Baada ya kubaini ubora wa mtaala, ni muhimu pia kutathmini ufanisi wake baada ya kutekelezwa.

Shriven anaiita hii pay-off evaluation, ambapo matokeo hufafanuliwa wazi.

Mthamini huzingatia athari za mtaala kwa:

Wanafunzi

Walimu

Wasimamizi

Wazazi

Mbinu hii inaweza kujumuisha kulinganisha:

Matokeo ya kabla na baada ya kufundishwa (pre-test & post-test)

Makundi ya majaribio na udhibiti

Wafuasi wa mbinu hii hudai ndiyo tathmini bora zaidi kwani inaonyesha moja kwa moja athari za mtaala kwa mwanafunzi.

3. Tathmini ya Maendeleo (Formative) na Tathmini ya Jumla (Summative)

FORMATIVE EVALUATION

Ni shughuli zote zinazofanyika ili kuboresha programu iliyopo.

Data hukusanywa ili kusaidia kufanya maamuzi ya marekebisho wakati mtaala unapotengenezwa.

Wakati wa hatua za awali za majaribio, tathmini hutoa taarifa za mara kwa mara na za kina kuongoza watengenezaji kufanya maboresho.

Mfano: Wakati wa kuunda mtaala, mthamini anaweza kupima uhalali wa maudhui na kupendekeza marekebisho.

Lengo ni:

Kusaidia uundaji

Kuboresha mtaala kabla ya kusambazwa kitaifa

Kutambua athari zinazotarajiwa na zisizotarajiwa

Inatumia mrejesho na marekebisho ili kuweka mchakato wa maendeleo ya mtaala wazi.

SUMMATIVE EVALUATION

Lengo lake ni kupata picha kamili kuhusu ubora wa mtaala uliokamilika.

Hufanyika baada ya mtaala kutekelezwa kitaifa.

Mazingatio makuu ni ufanisi wa mtaala mzima.

Huwawezesha wadau kutathmini jinsi mtaala ulivyofanya kazi.

Hutoa ushahidi kuhusu athari za sehemu zote ndogo ndogo za mtaala.

Inaweza kufanyika baada ya:

Hatua ya majaribio

Kabla ya utekelezaji wa mwisho

Husaidia kupata picha kamili ya bidhaa ya mtaala inavyoendelea.

Mchakato kwa kawaida:

Kubuni → Kuendeleza sehemu ndogo → Kujaribu (Pilot) → Kutekeleza → Kutathmini

Formative evaluation hutumia mbinu zisizo rasmi za ukusanyaji data.

Summative evaluation hutumia mbinu rasmi:

Zana zilizoundwa vizuri

Vipimo vilivyosanifiwa kupima malengo

Taratibu za uchambuzi zilizo wazi

A

METHODOLOGICAL ISSUES IN EVALUATION

-Evaluators need to measure how students are performing at the conclusion of the programme between M&E the programe and evaluating the students.

-Programme evaluation centers an instructional outcomes in the programme and determines whether this outcomes are as a result of groups of students experiencing the programme.

-The thrust of such evaluation is on the programme. It assesses the worth of a programme and holds those who deliver it accountable.

-Students evaluation is contrast involves gathering data about students performance to decide whether they are qualified for course completion or for graduation.

-The burden of responsibility shifts to the individuals students.

-If evaluators take their stand they really have no reason to modify the programme or to hold teachers accountable.

-The person an evaluator holds accountable offers reflects the individuals philosophical and political view of schools and society.

NORM REFERENCE AND CREITERION REFERENCED MEASUREMENT

Most evaluators of the curriculum involve achievement testing. Many norm reference tests sometimes called standardized tests have been created to discriminate among individual students. Although testing such discrimination is important in certain situations testing discrimination among curricular is necessary as well.

-Two basic approaches to testing dominate curriculum evaluation.

- Norm-referenced test

- Criterion reference test

Norm-reference test

-In this approach the student performance in a particular test is compared with the performance of other student who also took the same test (norming group) A-B standardized achievement test probably the most well- known norm reference test. Identify persons of varying ability. They have however questionable value for measuring the quality of a curriculum.

-They do not address the goals or content of a particular curriculum. They produce scores that are fairly global in nature such as reading comprehensions and maths computation. They are also not designed for a particular audience, what they measure is what a student knows in relation to other students at a given time. In addition standardized test are administered to determine the success of curriculum in place or a new curriculum.

-Is our KCSE a norm reference test?

CRITERION REFERENCE TEST

-This reports how a student starts with respect to some fixed criterion.

-This kind of a test indicates a learners status with respect to a learning task that can be stated in some specific educational objectives eg ability to identity particular examples of certain concepts or ability to multiply two digit numbers. With the criterion test a student is given a score that indicates either mastery or non-mastery of each objective.

M and E MODELS/HEORIES

Model is a copy of something that is usually smaller than the real.

-A theory is a contemplative and rational type of abstract or generalizing thinking or the result of such thinking

1Ralph Tyler.Eight year study evaluation model:

-This was the first major evaluation study conducted on curriculum. It is also the longest longitudinal study ever conducted on a large scale.

- The study lasted for 8 yrs from 1933 to 1941. A variety of methods were used to collect data, tests, questionnaires case study, interviews check lists, test, scales and inventories.

-In total 30 high schools were involved in the project. Through this study Tyler came up with the following recommendations in the conduct of an educational evaluation study.

-He says the first thing was to-:

1 Establish broad goals or objectives.

2)Classify the objectives

3)Define the objectives in behavioural terms.

- Find situation in which the achievements of the objectives can be shown.

- Develop/select the measurement, techniques(objectives/content/teaching methods, evaluation)

- Collect student performance data.

- Compare the data with the behaviorally stated objectives.

- Recomendations

-The steps in Tyler model/theory encourage evaluators to attend primarily to objectives that is, are the objectives achieved?

-    if they are achieved not achieved the evaluators then make appropriate decision.

Tayler maintain that evaluation is a recurring process and that evaluation feedback is used to re-formulate or re-define the set objectives

- information gathered is plugged back in to the curriculum. This recycling keeps the evaluation system dynamic and therefore the programme is seen to operate at optimal levels.

B

A

MASUALA YA KIMBINU KATIKA TATHMINI (METHODOLOGICAL ISSUES IN EVALUATION)**

Wathamini wanahitaji kupima jinsi wanafunzi wanavyofanya mwishoni mwa programu kwa kutofautisha kati ya kutathmini programu yenyewe na kutathmini wanafunzi.

Tathmini ya programu hujikita katika matokeo ya ujifunzaji ndani ya programu na kubaini ikiwa matokeo hayo yanatokana na kundi la wanafunzi waliopitia programu hiyo.

Lengo kuu la tathmini hii ni programu yenyewe. Inapima thamani ya programu na kuwawajibisha wale wanaoitekeleza.

Tathmini ya wanafunzi, kwa upande mwingine, inahusisha kukusanya data kuhusu utendaji wao ili kuamua kama wamehitimu kumaliza kozi au kuhitimu shahada.

Hivyo, jukumu la uwajibikaji linahamia kwa mwanafunzi binafsi.

Ikiwa wathamini wataegemea upande wa tathmini kwa wanafunzi pekee, hawana sababu ya kurekebisha programu au kuwawajibisha walimu.

Mtu anayeshikiliwa kuwajibika na mthamini huonyesha mtazamo wake wa kifalsafa na kisiasa kuhusu shule na jamii.

VIPIMO VYA NORM-REFERENCED NA CRITERION-REFERENCED

Wathamini wengi hupima mafanikio ya wanafunzi. Vipimo vya norm-referenced (mara nyingi huitwa vipimo sanifu) huundwa ili kutofautisha wanafunzi kulingana na uwezo. Hata hivyo, kupima ubora wa mtaala pia ni muhimu.

Kuna mbinu mbili kuu za upimaji katika tathmini ya mtaala:

i) Norm-Referenced Test (NRT)

Katika njia hii, matokeo ya mwanafunzi kwenye jaribio huliganishwa na matokeo ya wanafunzi wengine walioufanya mtihani huo (kundi la marejeo – norming group).

Mfano: mitihani ya kiwango cha taifa kama ile ya kusoma au hesabu.

Madhumuni yake ni kubaini tofauti za uwezo kati ya wanafunzi.

Haina thamani kubwa katika kupima ubora wa mtaala kwa sababu:

Haijengi kulingana na malengo ya mtaala maalum.

Hutoa alama za jumla kama kusoma kwa ufahamu au hesabu.

Haitengenezwi kwa hadhira mahususi bali kwa kulinganisha wanafunzi kwa wakati fulani.

Pia vipimo sanifu hutumiwa kupima kama mtaala uliopo au mpya unaendelea vema.

Swali la kuzingatia: Je, KCSE ni mtihani wa norm-referenced?

ii) Criterion-Referenced Test (CRT)

Hapa alama za mwanafunzi hulinganishwa na kiwango maalum (criterion), sio wanafunzi wengine.

Hupima kama mwanafunzi amekamilisha kikamilifu jukumu la ujifunzaji linaloendana na malengo fulani ya kielimu.

Mfano:

Uwezo wa kutambua mifano ya dhana fulani

Uwezo wa kuzidisha namba mbili za tarakimu

Mwanafunzi hutolewa alama zinazoonyesha kama amepata umahiri (mastery) au hajapata umahiri (non-mastery) kwa lengo fulani.

MIUNDO/MODELI NA Nadharia ZA M&E (M AND E MODELS/THEORIES)

Model ni nakala au mfano wa kitu halisi kwa ukubwa mdogo.

Theory ni fikira za kiakili zinazotafakari au kujumlisha dhana kuhusu jambo fulani.

1. Mfano wa Tathmini wa Ralph Tyler – “Eight Year Study Evaluation Model”

Huu ulikuwa utafiti mkuu wa kwanza wa tathmini ya mtaala. Pia ndiyo utafiti wa muda mrefu zaidi kuwahi kufanywa kwa kiwango kikubwa.

Utafiti uliendelea kwa miaka 8 (1933–1941).

Mbinu mbalimbali zilikuwa:

Mitihani

Dodoso

Utafiti wa kina (case study)

Mahojiano

Fomu za ukaguzi

Mizani na orodha za tabia

Shule 30 za upili zilishiriki.

Kupitia utafiti huu, Tyler alipendekeza hatua zifuatazo katika kufanya tathmini ya kielimu:

Hatua za Tyler:

Kuanzisha malengo mapana.

Kugawa malengo katika makundi.

Kufafanua malengo katika tabia zinazopimika (behavioural terms).

Kutafuta hali zinazoonyesha kufikiwa kwa malengo.

Kuunda/kuchagua mbinu za kupima (maudhui, malengo, mbinu za ufundishaji, tathmini).

Kukusanya data za utendaji wa wanafunzi.

Kulinganisha data na malengo yaliyowekwa katika mfumo wa kitabia.

Kutoa mapendekezo.

Msingi wa Tyler

Hatua hizi zinahimiza wathamini kuzingatia zaidi malengo.

Je, malengo yametimizwa? Yakitimia au yasipotimia huongoza kufanya maamuzi sahihi.

Tyler anaamini tathmini ni mchakato unaojirudia, na mrejesho wa tathmini hutumika kuboresha au kufafanua upya malengo.

Taarifa inayokusanywa hurudishwa kwenye mtaala na kuufanya ushindwe kudumaa — mfumo wa tathmini unakuwa hai na programu inafanya kazi kwa kiwango bora.

A

2. Metfessel – Michael evaluation model.

-In the late 1960’s metfesel and micahel presented a variation of Tycerian evaluation model.

-Their model represents and major steps in the evaluation process.

1. Involve both directly and indirectly members comprising of total educational community eg parents, students (learners) teachers, educational administrators, sponsors other organizational interested in the education. Professional lay citizens who are tax payers’ politiciansetc.

2. Develop a coersive aaray of broad goals and specific objectives and arrange them hierachy from general to specific outcome. Develop goals and specific objectives arranging.

3. Translate the specific objectives produced in step 2 in to a form that will be other communicable and applicable to the conduct of curriculum programme (step 3 in Tyler)

4. Create the instrumentation necessary to furnish criterion measures from which individual can draw inferences regarding the programmes effectiveness in the light of objectives stated (step 5 in Tyler?)

5. Conduct periodic observation throughout the implementation and maintenance of the programme using tests, cases and other appropriate instruments(step 6 of Tyler)

6. Analyze data gathered employing appropriate statistical procedures (step 6 of Tyler),

7. Interpret data in terms of particular judgementalstandards and values that reflect the philosophical orientation of the curriculum.

- The conclusion derived from such interpretation will enable those involved in the evaluation to judge the direction of learners growth and their progress in specific areas of education and the overall effectiveness of the total programme and its impact upon or affected parties (interprete step 6 of Tyler)

8. On the basis of the information gathered generate, recommendation that will varnish a basis for implementing the programme or for modifying the elements of curriculum eg objectives, contents, teaching methods, evaluation /assessments procedures etc recommendations

-At the conclusion of this step the process is ready to be repeated equivalent to number (7 of the Tyler)

SUMMARY

- Gather information from the total education in community.

- Develop goals and specific objectives and arranging them

- Translate

- Instrument development

- Data collection

- Data analysis

- Interprete, make conclusion

- Recommendations

ASSIGNMENTS

Compare Tyler model and Metfessel- Michael evaluation model.

SIMILARITIES

1Both models address on broad objectives then narrow them down to specific objectives stated in behavior terms.

2. Both use techniques to collect data.

3. Both are administered in situations of programme(existing)

4. Both models analyze the data collected. Tyler uses compare which Michael use analysis

5. Sequencial in both.

DIFFERENCES

1.Michael-metftesel model is a modification of Tyler.

2. Tyler model does not tell us where they have derived their objectives. Michael from community.

3. Recommendation in metffesel Tyler not there

4. 8 steps in metffesel, -Tyler 7 steps

5. Tyler uses traditional method Michael uses participatory

6. Tyler summative only Michael summative and formative

PROVUS DISCREPANCY EVALUATION MODEL

-The model developed by Malcom Provus. He combines evaluation with systems management theory and consists of 4 component and five stages of evaluation.

B

A. Muundo wa Tathmini wa Metfessel–Michael

Mwishoni mwa miaka ya 1960, Metfessel na Michael walitoa mabadiliko ya mfano wa tathmini wa Tyler.

Muundo wao unaonyesha hatua kuu katika mchakato wa tathmini.

Hatua za mchakato wa tathmini

Kuhusisha wanajamii wote wa elimu moja kwa moja na kwa njia isiyo ya moja kwa moja.

Mfano: wazazi, wanafunzi, walimu, wasimamizi wa elimu, wafadhili, wadau wa elimu, wananchi wa kawaida wanaolipa kodi, wanasiasa n.k.

Kuandaa mkusanyiko wa malengo mapana na malengo mahususi, na kuyaweka katika mpangilio wa mlolongo kuanzia matokeo ya jumla hadi mahususi.

Kutafsiri malengo mahususi yaliyoandaliwa katika hatua ya 2 katika mfumo ambao unaweza kuwasilishwa kirahisi na kutumika katika utekelezaji wa programu ya mtaala (sawa na hatua ya 3 kwa Tyler).

Kutengeneza vifaa na vyombo vya vipimo (instrmentation) vinavyohitajika kupima viwango vinavyotumika kutoa hitimisho kuhusu ufanisi wa programu kulingana na malengo yaliyotajwa (sawa na hatua ya 5 ya Tyler).

Kufanya uchunguzi wa mara kwa mara wakati wa utekelezaji na uendelezaji wa programu kwa kutumia mitihani, kisa elezi na vyombo vingine vinavyofaa (sawa na hatua ya 6 ya Tyler).

Kuchambua data iliyokusanywa kwa kutumia mbinu sahihi za takwimu (sawa na hatua ya 6 ya Tyler).

Kufasiri data kulingana na viwango na thamani za kimahusiano zinazoakisi falsafa ya mtaala.

Hitimisho litokanalo na tafsiri hiyo litawasaidia wanaohusika katika tathmini kutathmini mwelekeo wa maendeleo ya wanafunzi, maendeleo yao katika maeneo mahususi ya elimu, na ufanisi wa jumla wa programu kwa washikadau wote.

Kutokana na taarifa iliyokusanywa, kutoa mapendekezo yatakayowezesha utekelezaji wa programu au kurekebisha vipengele vya mtaala kama vile:

malengo

maudhui

mbinu za ufundishaji

mbinu za tathmini n.k.

Mwishoni mwa hatua hii, mchakato uko tayari kurudiwa (sawa na hatua ya 7 kwa Tyler).

MUHTASARI

Kukusanya taarifa kutoka kwa jamii nzima ya elimu.

Kuandaa malengo mapana na mahususi na kuyaweka kwa mlolongo.

Kutafsiri malengo.

Kuandaa vifaa vya vipimo.

Ukusanyaji wa data.

Uchanganuzi wa data.

Ufafanuzi na uamuzi.

Mapendekezo.

KAZI YA ZIADA (ASSIGNMENT)

Linganisheni mfano wa Tyler na mfano wa tathmini wa Metfessel–Michael.

Similarities (Sifa zinazofanana)

Mifano yote miwili hushughulikia malengo mapana yakipunguzwa hadi malengo mahususi yaliyo katika tabia.

Zote hutumia mbinu za kukusanya data.

Zote hutumika katika programu zilizo tayari zipo.

Zote huchambua data iliyokusanywa—Tyler hutumia kulinganisha, Michael hutumia uchambuzi.

Zote ni za hatua mfululizo (sequential).

Differences (Tofauti)

Mfano wa Metfessel–Michael ni mapendekezo mapya ya mfano wa Tyler.

Tyler haelezi mahali ambapo malengo yamepatikana; Metfessel hutumia jamii kutengeneza malengo.

Mfano wa Metfessel una hitaji la mapendekezo; Tyler halina.

Metfessel ana hatua 8; Tyler ana hatua 7.

Tyler hutumia mbinu za jadi; Metfessel hutumia ushirikishwaji (participatory).

Tyler ni wa tathmini ya jumla (summative), Metfessel ni wa jumla na endelevu (summative + formative).

MFANO WA TATHMINI YA PROVUS (PROVUS DISCREPANCY EVALUATION MODEL)

Mfano huu uliundwa na Malcolm Provus.

Unachanganya tathmini na nadharia ya usimamizi wa mifumo.

Una sehemu kuu nne na hatua tano za tathmini.

A

THE FOUR COMPONENTS ARE

1. Determining programme standards

2. Determining programme performance.

3. Comparing programme performance with standards

4. Determining whether a discrepancy exists between programme standards and performance.

- Discrepancy information is reported to decision makers who inturn must make a decision or act at each stage.

-This choice of decisions at each stage are either to go to the next stage, recycle to a previous stage or start the programme over again, modify performance or standards or terminate the programme.

-It is the job of the evaluator to report to the decision maker and to identify problems and suggest what corrective actions are possible. When discrepancy exists the decision maker is the key person in the discrepancy model. There are five stages in this model.

| STAGE | PERFOMANCE | STANDARD |
| --- | --- | --- |
| 1 | Design | Design criteria |
| 2 | Installation | Installation fidelity |
| 3 | Processes | Process adjustment |
| 4 | Product | Product assessment |
| 5 | Cost | Comparison and cost benefits |

In all the five stages programme performance is compared to programme standards which have already been established.  These are:

- Design stage

-This involves a comparison of the programmed design with a design(criterion) standard.

-The programme is examined to determine if it internally sound (Adequancy of space, personnel, resources, materials) and externally sound (comparison with similar programmes that seem to work)

-The initial problems of the programme are identified,any discrepancy that exists between the programme design and design standards is reported to the decision maker who decides whether the programme should be modified, rejected or accepted.

2. Installation stage

- The actual operation of the programme is compared with the installation standards

-The characteristics of the programme are evaluated including facilities media methods student’s abilities and staff qualifications discrepancy between programme installation and installation criteria standards are noted and reported to the decision makers for appropriate action (implementation stage)

3. Processes stage.

-Specific programme, processes are evaluated including students and staff activities, functions and communications.

-If the processes are inadequate. This is reported to the decision maker who should take/make the appropriate action.

4. Product stage

-The effects of the whole programme is evaluated in terms of the original goals.The products to be assessed can be in terms of students and staff product as well as products related to the school and community.

-The information gained will assist decision makers about whether the programme is worthy while and should be continued as; modified or terminated.

5. Cost stage

-The programme products should be compared to product of similar programmes. It should also be evaluated in terms of cost benefits.

- Provus however does not explain clearly the methods of evaluation cost benefits analysis. However we must always ask ourselves whether the results are worthy the cost not only in terms of money but also morale and time taken away from other tasks. This answer has economic, social and political implications.

Provus claimed that his evaluation plan can be used to make evaluation of ongoing programmes in any stage from the planning to the implementation.

ASSIGNMENT

Tylerian evaluation model.

Discuss in your own areas and show the extent to which it is applicable to the Kenyan education system.

B

A. VIPENGELE VYENNE (THE FOUR COMPONENTS)

Kuweka viwango vya programu

Kuweka utendaji halisi wa programu

Kulinganisha utendaji wa programu na viwango vilivyowekwa

Kubaini kama kuna pengo (discrepancy) kati ya viwango vya programu na utendaji wa programu.

Taarifa kuhusu tofauti (discrepancy) hutolewa kwa watunga maamuzi ambao wanapaswa kufanya uamuzi katika kila hatua.

Uchaguzi wa maamuzi katika kila hatua unaweza kuwa:

kuendelea na hatua inayofuata,

kurudia hatua ya awali,

kuanzisha upya programu,

kurekebisha utendaji au viwango,

au kusitisha programu.

Kazi ya mtathmini (evaluator) ni kuripoti kwa mtunga maamuzi, kubaini matatizo na kupendekeza hatua sahihi za kurekebisha.

Pindi tofauti inapojitokeza, mtunga maamuzi ndiye mtu muhimu zaidi katika modeli hii.

HATUA TANO ZA MFANO WA PROVUS

HATUA	UTENDAJI (Performance)	KIWANGO (Standard)

1	Ubunifu (Design)	Vigezo vya muundo (Design criteria)

2	Ufungaji/utekelezaji wa awali (Installation)	Uaminifu wa ufungaji (Installation fidelity)

3	Michakato (Processes)	Marekebisho ya mchakato (Process adjustment)

4	Bidhaa/matokeo (Product)	Tathmini ya bidhaa (Product assessment)

5	Gharama (Cost)	Ulinganisho wa gharama na manufaa (Cost–benefit comparison)

Katika hatua zote tano, utendaji wa programu hulinganishwa na viwango vya programu ambavyo tayari vimewekewa viwango.

1. Hatua ya Muundo (Design stage)

Inahusisha kulinganisha muundo wa programu na viwango vya muundo (design criteria).

Programu hukaguliwa ili kubaini kama ina uhalali wa ndani:

nafasi,

wafanyakazi,

rasilimali,

vifaa.

Pia hukaguliwa kwa uhalali wa nje:

kulinganisha na programu zingine zinazofanya vizuri.

Matatizo ya awali hutambuliwa.

Tofauti yoyote kati ya muundo wa programu na viwango vya muundo huripotiwa kwa mtunga maamuzi ambaye ataamua kama programu ibadilishwe, ikataliwe au ikubalike.

2. Hatua ya Ufungaji (Installation stage)

Utekelezaji halisi wa programu unalinganishwa na viwango vya ufungaji.

Vipengele vinavyokaguliwa ni pamoja na:

miundombinu,

vifaa vya kufundishia,

mbinu za ufundishaji,

uwezo wa wanafunzi,

sifa za walimu.

Tofauti kati ya ufungaji halisi na viwango vya ufungaji huripotiwa kwa mtunga maamuzi kwa hatua sahihi kuchukuliwa (hatua ya utekelezaji).

3. Hatua ya Michakato (Processes stage)

Michakato mahususi ya programu hutathminiwa ikiwa ni pamoja na:

shughuli za wanafunzi,

shughuli za walimu,

majukumu,

mawasiliano.

Iwapo michakato haifanyi kazi ipasavyo, taarifa hutolewa kwa mtunga maamuzi kwa ajili ya marekebisho.

4. Hatua ya Bidhaa (Product stage)

Matokeo ya programu nzima hutathminiwa kulingana na malengo ya awali.

Bidhaa zinazotathminiwa huweza kuwa:

matokeo ya wanafunzi,

utendaji wa walimu,

matokeo ya shule,

athari kwa jamii.

Taarifa hii husaidia watunga maamuzi kuamua kama:

programu iendelee ilivyo,

ibadilishwe,

au isitishwe.

5. Hatua ya Gharama (Cost stage)

Bidhaa za programu hulinganishwa na bidhaa za programu zinazofanana.

Tathmini pia inazingatia uwiano wa gharama na manufaa (cost–benefit analysis).

Ingawa Provus hakueleza mbinu mahsusi za kufanya cost–benefit analysis, anasisitiza kujiuliza:

Je, matokeo yanastahili gharama?

Hii inajumuisha gharama za:

fedha,

muda,

morali,

fursa nyingine zilizopotea.

Jibu lina athari za kiuchumi, kijamii na kisiasa.

Provus alisisitiza kuwa mpango wake wa tathmini unaweza kutumika kutathmini programu yoyote iliyo katika hatua yoyote kati ya upangaji na utekelezaji.

ASSIGNMENT (KAZI YA NYUMBANI)

Mfano wa tathmini wa Tyler (Tylerian Evaluation Model):

Jadili katika muktadha wa maeneo yako na uonyeshe kiwango ambacho unafaa kutumika katika mfumo wa elimu wa Kenya.

A

STAKES RESPONSIVE EVALUATION MODEL.

-Responsive evaluation is a term popularized by Robert stake and he is more concerned with evaluating curriculum or programme of activities and processes than intent on outcomes.

-It relies more on informal and natural communication. It is concerned with the portrayed of the programme than standardized data, test scores and goals (responses and expected from different audiences learners, teachers and parents).

-Responsive evaluation requires planning and development but relies less on formal statements and research oriented information.

-Using the responsive approach the evaluation tells the story of a programme describes the clients, and personnel, presents its features and identifies major issues and problems and reports the accomplishment.

- The evaluator assumes the role of a critique reviewing a play. Stake maintains that the evaluator must develop a plan which deals with the scope and activities of the programme.

- He/she must arrange for people to make observations, prepare narratives, portrays and provide product displays because all of us have particular biases, the various audiences of the report must be identified and their feelings and expressions of what is worthwhile and important to be considered.

-The data reported must be analyzed in terms of the audience biases and they must have a chance to react to the findings.

-Stakes outlines the ten steps of responsive evaluation and applied to evaluating a curriculum.These are:

1. Negotiate a frame work for evaluation with sponsors.

2. Find out topics issues and questions of concern from the sponsors (go to the specific of what is contained in the in the framework.)

3. Formulate questions for guiding the evaluation.

4. Identify the scope and activities of the curriculum the needs of clients and personnel (educational clients) clients – consumers personnel – teachers/administrators.

5. Observe, discuss and prepare case studies.

6. Put down the information and identify the major issues or questions.

7. Present initial findings in a tentative report.

8. Analyze reactions and investigate pre-dominant concern more carefully/ sponsors and the ones to be given the findings)

9. Look for conflicting evidence that would ‘invalidate’ findings as well as collaborative evidence that would support findings.

10.Report the results

-Many of these steps are related to goal free evaluation which is concerned with biases of evaluation. In goal-free evaluation the evaluator is expected to be objective not influenced by the goals or objectives of the programme developed by sponsors.  Planning but relies less on research

STAKES CONQRUENCE – CONTIGENCY EVALUATION MODEL

-Robert stake distinguishes between formal and informal evaluation procedures while recognizing the educational evaluation continues to depend on casual observations implicit goals, intuitive norms and subject judgment. He notes that educator should strive to establish more formal evaluation procedures.

-Formal procedures are objective and aim at furnishing data so that descriptions can be made and judgmentsrendered. Regarding the programme being evaluated.

-In addition to collecting and reporting on handed data, stake states that evaluators collect and process more extensive types of data and that they consider the dynamics among the people involved in the curriculum process.

-stakes maintains that curriculum evaluator must make judgement in addition to reporting data.

-He points out that making judgment is part of the professional role of an evaluator.

-Stakes maintains that data can be organized into 3 bodies of information.

These are:

1.Antecedents inputs (entry behavior

2. Transactions – process – interactives between and among learners achievements (motorskills)

3. Outcomes

ANTECEDENTS

Antecedent is any condition that exists prior to teaching and learning that may impact on outcomes for example status or administrative characteristics of the students prior to their lessons, their aptitudes, previous achievement, scores, grades, discipline, attendance  etc.

-Antecedents also include teaching characteristics eg years of experience, type of education, their age, qualifications, gender, attitude, behavior rating (antecedent are simply entry behavior on inputs)

B

A. MFANO WA TATHMINI WA STAKE UNAOTEGEMEA UITIKIAJI (STAKES RESPONSIVE EVALUATION MODEL)

Responsive evaluation ni dhana iliyoenezwa na Robert Stake, na inalenga zaidi kutathmini mtaala au programu kwa kuangalia shughuli na michakato, badala ya kuzingatia tu matokeo.

Inategemea zaidi mawasiliano yasiyo rasmi na ya kiasili, na inalenga kuonesha uhalisia wa programu kuliko kutumia data sanifu, matokeo ya mitihani au malengo pekee (inazingatia maoni ya hadhira mbalimbali—wanafunzi, walimu na wazazi).

Ingawa tathmini hii inahitaji mipango na uundaji, haitegemei sana taarifa rasmi au tafiti za kitaaluma.

Kwa kutumia mbinu hii, tathmini inaeleza hadithi ya programu:

inamwelezea mteja (wanafunzi),

wafanyakazi (walimu/maafisa),

vipengele vya programu,

masuala muhimu na changamoto,

na mafanikio yaliyopatikana.

Mtathmini huchukua nafasi kama mkosoaji anayepitia tamthilia. Stake anasisitiza kuwa mtathmini lazima aandae mpango unaohusu upeo na shughuli za programu.

Mtathmini lazima apange watu wafanye uchunguzi, waandae simulizi, maelezo ya kina (portraits), na manyunyu ya matokeo (product displays).

Kwa kuwa kila hadhira ina upendeleo (bias), ni muhimu kutambua makundi yote ya hadhira na kuzingatia hisia na maoni yao kuhusu kilicho muhimu.

Taarifa zinazotolewa lazima zichanganuliwe kulingana na upendeleo wa hadhira, na hadhira inapaswa kuwa na nafasi ya kujibu na kutoa maoni kuhusu matokeo.

Hatua Kumi za Tathmini ya Stake

Kukubaliana kuhusu mfumo wa tathmini pamoja na wadhamini (sponsors).

Kubaini mada, masuala na maswali ya umuhimu kwa wadhamini.

Kutunga maswali yatakayoongoza tathmini.

Kutambua upeo na shughuli za mtaala pamoja na mahitaji ya wateja na wafanyakazi (wateja = wanafunzi; wafanyakazi = walimu/watawala).

Kufanya uchunguzi, majadiliano na kutayarisha tafiti za kesi (case studies).

Kuweka taarifa kwa maandishi na kubaini masuala makuu.

Kuwasilisha matokeo ya awali katika ripoti ya muda (tentative report).

Kuchanganua maoni ya waliopokea ripoti na kuchunguza kwa undani masuala yao ya msingi.

Kutafuta ushahidi unaopingana (invalidate findings) na ushahidi unaounga mkono matokeo.

Kuripoti matokeo ya mwisho.

Hatua hizi nyingi zinafanana na goal-free evaluation, ambayo inalenga kupunguza upendeleo wa mtathmini kwa kutoegemea malengo rasmi ya programu.

STAKES CONGRUENCE–CONTINGENCY EVALUATION MODEL

Robert Stake anafanya utofautishaji kati ya mbinu za tathmini rasmi na zisizo rasmi, akitambua kuwa tathmini katika elimu bado inategemea:

uchunguzi wa kawaida (casual observations),

malengo yasiyo wazi,

viwango vya kijanja (intuitive norms),

na maamuzi ya kibinafsi ya wataalamu.

Anasisitiza kuwa waelimishaji wanapaswa kujitahidi kuanzisha taratibu za tathmini rasmi.

Mbinu rasmi ni lengo, na inalenga kutoa data inayowezesha kufanya maelezo na kutoa hukumu kuhusu programu inayotathminiwa.

Mbali na kukusanya na kuripoti data ya ziada, Stake anasisitiza kuwa mtathmini anapaswa:

kukusanya aina pana zaidi za data,

kuzingatia mienendo kati ya watu wanaohusika na mchakato wa mtaala.

Stake anasema kuwa mtathmini wa mtaala anapaswa kutoa hukumu, si kuripoti data pekee—hii ni sehemu ya wajibu wa kitaaluma wa mtathmini.

Stake anaamini kuwa data inaweza kuandaliwa katika makundi matatu ya taarifa:

1. Antecedents (Vigezo vya awali / hali kabla ya kujifunza)

Antecedents ni hali yoyote iliyokuwepo kabla ya ufundishaji na ujifunzaji, ambayo inaweza kuathiri matokeo ya mwisho. Mfano:

hali ya wanafunzi kabla ya masomo,

tabia zao,

uwezo wao (aptitudes),

mafanikio ya awali,

alama,

nidhamu,

mahudhurio.

Antecedents pia zinahusisha sifa za walimu, kama:

uzoefu wa miaka,

kiwango cha elimu,

umri,

sifa/maarifa,

jinsia,

mtazamo na tabia.

Kwa kifupi, antecedents ni hali ya kuanzia (entry behavior/input conditions).

A

TRANSACTIONS

Stakes notes that transactions between and among students and teachers, students and resource people.

-Transactions are interactions the students have with certain curriculum, materials and classroom environment dealing with time allocation, space arrangement and communication flourish school. Top to bottom, bottom to top, horizontal communication etc space available.

-Transactions are what is commonly referred to as process of teaching and instruction (conative –to find out what is present tomorrow.

OUTCOMES

Outcomes are the products of the programmes particularly the achievements. Sometimes attitudes, motor skills.

-Evaluators also need to attend to such outcomes as the impact of a new programme on teachers, perceptions of their competence.

-They need to evaluate the influence of aprogramme outcomes on the actions of administrators.

-They may also need to consider outcomes that are not directly evident at the conclusion of a programme.

-Stake commends that outcomes are the consequences immediate and long term range.

-Coginitive and conatives, personal and community wide.

-Stakes model for planning and evaluation study provides an organizational framework that points out data to be considered and contrasts what is planned and what has occurred,

-This model shows that antecedents, transactions and outcomes (the elements of evaluation) both intended and observed.

-The evaluator collects various judgments from different parties eg students, support staff and community members and makes descriptions to fill in the matrix.

-The challenges to the evaluators is to identify contingencies and later contingencies among those antecedents, transactions and outcomes.

ORGANIZATIONAL FRAMEWORK OF C.C MODEL

| PROGRAMME ELEMENTS | DESCRIPTION MATRIX INTENTS OBSERVED | JUDGEMENT MATRIX STANDARDS JUDGEMENT |
| --- | --- | --- |
| ANTECEDENTS TRANSACTIONS OUTCOMES |  |  |

- Stakes proposes that for each of the three elements the evaluator records intents (planned goals) the observation made(operations) the standards (criteria for judgement) and then the judgment reached.

- Contingencies are the relationship among the variables in the three categories. Ideally it should be demonstrated that the outcomes are as a result of antecedents and transactions that is one category is expected to lead to observable and/or measurable variable in another category.

- Evaluators are therefore challenged to identify the outcomes that are contingent upon particular antecedents phenomenon occurring in specific transactions.

- -The model shows that the evaluators are also concerned with contingency between the intended and the observed outcomes. In dealing with contingency the evaluator strikes to match what is intended and what is observed.

- The key question is “did what was intended actually happened?’ To be completely congruent all of the intended antecedents, transactions and outcomes would have to occur.

B

A

TRANSACTIONS (MIINGILIANO)**

Stake anabainisha kwamba miingiliano (transactions) hutokea kati ya wanafunzi na walimu, na pia kati ya wanafunzi na watu wa rasilimali mbalimbali.

Transactions ni mwingiliano wa wanafunzi na mtaala, vifaa vya kujifunzia na mazingira ya darasa, vinavyohusisha mgawanyo wa muda, mpangilio wa nafasi, na aina za mawasiliano shuleni (mawasiliano kutoka juu kwenda chini, chini kwenda juu, au ya usawa).

Transactions ndizo zinachojulikana kama mchakato wa ufundishaji na ujifunzaji, yaani hatua zinazoonekana zinazofanyika wakati wa kufundisha (conative—kubaini kinachowezekana kutokea kesho).

OUTCOMES (MATOKEO)

Outcomes ni mazao ya programu, hususan mafanikio ya wanafunzi. Wakati mwingine hujumuisha:

mitazamo,

ujuzi wa mwili (motor skills),

tabia na uwezo ulioongezeka.

Mtathmini pia anapaswa kuzingatia:

Athari za programu mpya kwa walimu, kama vile mtazamo wao kuhusu uwezo wao wa kufundisha.

Athari za matokeo ya programu kwa vitendo na maamuzi ya wasimamizi.

Matokeo ambayo yanaweza yasijitokeze mara moja, bali baada ya muda fulani.

Stake anasisitiza kuwa outcomes ni matokeo ya muda mfupi na muda mrefu, yenye nyanja za:

kiakili (cognitive),

kitabia na kimotisha (conative),

binafsi na ya kijamii kwa upana.

Mfano wa Stake kwa kupanga na kutathmini unatoa muundo wa shirika (organizational framework) unaoonesha aina za data zinazopaswa kuzingatiwa na kulinganisha kile kilichopangwa na kile kilichotekelezwa.

Mfano huu unaonesha kuwa antecedents, transactions, na outcomes (vipengele vya tathmini)—vyote vinazingatiwa katika hali mbili:

zile zilizokusudiwa, na

zile zilizoonekana kihalisia.

Mtathmini hukusanya maoni kutoka kwa watu mbalimbali:

wanafunzi,

wafanyakazi wa usaidizi,

wanajamii,

na hutengeneza maelezo ya kuziba nafasi katika jedwali la tathmini.

Changamoto kubwa kwa mtathmini ni kubaini uhusiano wa utegemezi (contingencies) kati ya antecedents, transactions na outcomes—yaani kutambua ni vipengele vipi vinategemeana.

MUUNDO WA SHIRIKA WA MFANO WA C.C (ORGANIZATIONAL FRAMEWORK OF THE C.C MODEL)

VIPENGELE VYA MPANGO

Jedwali la Maelezo (Description Matrix)

Jedwali la Hukumu (Judgement Matrix)

Muundo wa Jedwali

PROGRAMME ELEMENTS (Vipengele vya Mpango)	INTENTS (Kilichokusudiwa)	OBSERVED (Kilichoonekana)	STANDARDS (Viwango)	JUDGEMENT (Hukumu)

Antecedents

Transactions

Outcomes

Maelezo Muhimu

Stake anapendekeza kwamba kwa kila kipengele (antecedents, transactions, outcomes), mtathmini anapaswa kurekodi:

Intents (malengo yaliyopangwa)

Observed (kile kilichoonekana kikitokea)

Standards (vigezo vya kufanya hukumu)

Judgement (hitimisho)

Contingencies ni uhusiano kati ya vipengele katika makundi haya matatu.

Kwa mfano, inapaswa kuonyeshwa kuwa outcomes zinatokana na antecedents na transactions.

Yaani, mojawapo ya vipengele hivi vinapaswa kupelekea kipimo au tukio kinachoonekana katika kingine.

Mtathmini anatakiwa kubaini outcomes zinazotegemea:

antecedents fulani,

na transactions maalumu.

Mfano unaonesha pia kwamba mtathmini anatakiwa kuzingatia tofauti kati ya matokeo yaliyokusudiwa na yale yaliyopatikana.

Swali muhimu ni:

"Je, kile kilichokusudiwa ndicho kilichotokea kweli?"

Kwa ulinganifu kamili (congruence), antecedents, transactions na outcomes zote zilizokusudiwa zinapaswa kutokea kama zilivyopangwa.

A

STUFFLEBEAMS CONTEXT INPUT PROCESS PRODUCT MODEL (CIPP)

-The most important contribution to a decision management oriented approach to education evaluation has been presented by Daniel stufflebeams.

-His approach to evaluation is recognized as the CIPP model. It considers evaluation tobe continuing process.

-The influence on decision of management operation relating to the curriculum are evaluated. These decisions in turn impact on programme activities or operations which in turn are evaluated. This is a continous process. The evaluation process includes three steps

:

1Delineating – information necessary for collection

2. Obtaining the information

3. Providing the information to interested parties.

- Any evaluation study must include this three steps.

-Stufflebeam noted that four types of decisions are required in evaluation effort. These are:

1. Planning decisions

2.Structuring decisions

3.Implementing decisions.

4.Recycling decisions.

-Corresponding to the decision types are four types of evaluation. These are

1.Context evaluation

2. Input evaluation

3. Process evaluation

4. Product evaluation.

CONTEXT EVALUATION

-Situational analysis.

-Context evaluation involves studying the environment in which the programme is run

-its purpose is to provide a rationale for determination of objectives. It defines the relevant environment, portrays the desired and actual conditions pertaining to the environment focuses for unmet needs and missed opportunities and diagnoses the reasons for unmet needs.

-Context evaluation is really a situational analysis. Context evaluation is not a onetime activity it continues to vanish data regarding the operations and accomplishment of the total system.

- Input evaluation

- This stage is designed to provide information for determining how to utilize resources and to meet programme goals. Input evaluators assess the schools capabilities to carry out the task of evaluation. They consider the strategies suggested to achieving programme goals and they identify the means by which a suggested strategy will be implemented.  At this stage they evaluate alternatives designs in terms of how they will contribute to the attainment of the objectives stated and in terms of their demands upon resources, time and budget. They consider them in the light of procedural visibility.

- -In contrast to context evaluation, input evaluation is ad hoc (temporary) and micro-analyticrather than systematic and macro analytic. It is placed into action in light of the conclusion reached from context evaluation. It evaluates specific aspects of the curriculum planned, input evaluation asks many questions. Eg

- 1. Are the objectives stated objectively?

- 2. Are the objectives congruent with the state goals and aims of the school? This is where the curriculum is implemented/

- 3. Is the content congruent with aims/goals objectives of the programme?

- 4. Are the instructional strategies appropriate?

- 5. Are the assessment methods suitable?

- 6. Do other strategies exists that can also help meet the goals?

- 7. What is the bases for believing that using this basis instructional strategies will enable educators to successfully attain their objectives (can do comparative analysis, theoretical bases)

PROCESS EVALUATION

This stage addresses curriculum implementation decisions that control or manage the plan or programme. It is used to determine the contingency between the planned and actual activities. Stufflebeam has presented three main strategies for process evaluation.

- To detect or predict defects in the procedural design or its implementation.

- To provide information for programmed decisions.

- To maintain a record of procedure as they occur.

PLAN OR PROGRAMME DEFECTS

-In dealing with plan or programme defects it is important for educators to identify and monitor continually the potential sources of the project failure.

-They must pay attention to the logistics of the entire operation and they must maintain communication channels among all affected parties.

-They must also consider the adequency of the resources that is physical facilities, staff preparations and time schedules.

INFORMATION FOR PROGRAMME DECISION

-The second strategy involves projecting and servicing programed decisions made by project managers during the implementation of a project. In this step, evaluators might make a decision regarding test development prior to the actual implementation of the programme. Some decisions may require that certain inservice activities be planned and carried out before the actual implementation of the programme.

B

A

MFANO WA CIPP WA STUFFLEBEAM (CONTEXT, INPUT, PROCESS, PRODUCT)**

-Mchango muhimu zaidi katika mbinu ya kufanya tathmini ya elimu inayotegemea usimamizi wa maamuzi umetolewa na Daniel Stufflebeam.

-Mbinu yake ya tathmini inajulikana kama Mfano wa CIPP. Inazingatia tathmini kama mchakato unaoendelea.

-Ushawishi wa maamuzi ya usimamizi kuhusu uendeshaji wa mtaala unafanyiwa tathmini. Maamuzi haya huathiri shughuli au uendeshaji wa programu ambazo pia hutathminiwa. Huu ni mchakato endelevu.

-Mchakato wa tathmini unajumuisha hatua tatu:

Kubainisha – taarifa muhimu zinazohitajika kukusanywa

Kupata taarifa

Kutoa taarifa kwa wadau wanaohusika

-Tathmini yoyote lazima ijumuishe hatua hizi tatu.

-Stufflebeam alitaja aina nne za maamuzi yanayohitajika katika juhudi za tathmini. Haya ni:

Maamuzi ya mipango

Maamuzi ya upangaji

Maamuzi ya utekelezaji

Maamuzi ya marejeleo (recycling)

-Kulingana na aina hizi za maamuzi, kuna pia aina nne za tathmini:

Tathmini ya Muktadha (Context Evaluation)

Tathmini ya Rasilimali Ingizi (Input Evaluation)

Tathmini ya Mchakato (Process Evaluation)

Tathmini ya Matokeo (Product Evaluation)

1. TATHMINI YA MUKTADHA (CONTEXT EVALUATION)

-Uchambuzi wa hali halisi.

-Tathmini ya muktadha inahusisha kuchunguza mazingira ambayo programu inaendeshwa.

-Lengo lake ni kutoa hoja ya kuweka malengo. Inafafanua mazingira husika, inaonyesha hali inayotarajiwa na hali halisi ya mazingira, inabainisha mahitaji ambayo hayajatimizwa, fursa zilizokosa kutumiwa, na kuchunguza sababu za mahitaji kutotimizwa.

-Kimsingi, ni uchambuzi wa hali.

-Tathmini ya muktadha si shughuli ya mara moja; ni endelevu kwa kukusanya taarifa kuhusu uendeshaji na mafanikio ya mfumo mzima.

2. TATHMINI YA RASILIMALI INGIZI (INPUT EVALUATION)

-Hatua hii inalenga kutoa taarifa kuhusu jinsi ya kutumia rasilimali ili kufanikisha malengo ya programu.

-Watathmini huangalia uwezo wa shule kutekeleza mchakato wa tathmini.

-Wanachunguza mikakati iliyopendekezwa kufikia malengo ya programu na kubaini jinsi itakavyotekelezwa.

-Katika hatua hii wanachambua miundo mbadala kwa kuzingatia mchango wake katika kutimiza malengo na mahitaji ya rasilimali, muda na bajeti.

-Wanazingatia pia uwezekano wa utekelezaji wa taratibu.

-Tofauti na tathmini ya muktadha, tathmini ya rasilimali ingizi ni ya muda mfupi (ad hoc) na ya uchambuzi mdogo.

-Inawekwa katika hatua ya utekelezaji kulingana na hitimisho la tathmini ya muktadha.

-Inauliza maswali kama vile:

Je, malengo yameandikwa wazi na kwa uangalifu?

Je, malengo yanaendana na malengo ya shule?

Je, maudhui yanaendana na malengo ya programu?

Je, mbinu za ufundishaji zinafaa?

Je, mbinu za tathmini zinafaa?

Je, kuna mbinu mbadala zinazoweza kusaidia kufikia malengo?

Ni msingi gani unaothibitisha kuwa kutumia mbinu fulani kutasaidia walimu kufikia malengo yao (mfano uchambuzi linganishi au msingi wa nadharia)?

3. TATHMINI YA MCHAKATO (PROCESS EVALUATION)

-Hatua hii inahusiana na maamuzi ya utekelezaji wa mtaala, ambayo huchunguza au kudhibiti utekelezaji wa mpango.

-Inatumika kubaini uhusiano kati ya shughuli zilizopangwa na zinazoendelea kwa vitendo.

-Stufflebeam alitoa mikakati mitatu ya tathmini ya mchakato:

Kugundua au kutabiri kasoro katika mpango au utekelezaji wake.

Kutoa taarifa kwa maamuzi ya programu.

Kuweka rekodi ya taratibu zinavyoendelea kufanyika.

KASORO KATIKA MPANGO AU PROGRAMU

-Wakati wa kushughulikia kasoro, walimu wanatakiwa kutambua na kufuatilia vyanzo vinavyoweza kusababisha kushindwa kwa mradi.

-Wanapaswa kuzingatia mipangilio ya shughuli nzima na kudumisha mawasiliano baina ya wadau.

-Wanapaswa pia kuzingatia ukamilifu wa rasilimali kama vile miundombinu, maandalizi ya wafanyakazi na ratiba za muda.

TAARIFA KWA MAAMUZI YA PROGRAMU

-Mkakati wa pili unahusu kutoa taarifa zinazosaidia katika maamuzi ya meneja wa mradi wakati wa utekelezaji.

-Katika hatua hii, watathmini wanaweza kuandaa maamuzi kuhusu utayarishaji wa mitihani kabla ya utekelezaji wa mpango.

-Baadhi ya maamuzi yanaweza kuhitaji kupanga na kutekeleza mafunzo ya ndani (in-service training) kabla ya kuanza kwa programu.

A

MAINTAINANCE OF RECORDS OF PROCEDURES.

-The third strategies addresses the main feature of project decision eg the particular content,selected the instructional strategies planned or the time allocated in the plan for such activities. Process evaluation which includes the times strategies occurs during the implementation stage of curriculum development. It is a piloting process conducted to ‘debug’ the programme before countrywide implementation.

PRODUCT EVALUATION

-Product evaluators gather data to determine whether the final curriculum product now in use is accomplishing what they had hoped. It answers questions such as:

-To what extent are the objectives created being attained? Product evaluation provides evaluators with information that will enable them to decide whether to continue, terminate or modify the new curriculum.

-It enables them to link actions at this stage of model to other stages of the total change process.

STAFFLEBEAM MACRO(TOTAL) EVALUATION MODEL

Stafflebeam has purposed a total evaluation programme. The model provides for systematic context input process and product evaluation.

The model also states that four types of decisions are necessary.

- Planning decision- are enacted after context evaluation.

- Structuring decisions are initiated after input evaluation

- Implementation decisions follow process evaluation

- Recycling decisions are made after production evaluation

-Staff beam notes that decision making occurs in 4 different settings

1.Small change with highly information

2. Small change with low information

3Large change with high information

4.Large change with low information

-The different settings in which decisions can be made generate four types of change activities.

1 Neomobolistic change. Occurs when some attempts to make large change on basis of low information. In such a case an innovative is being attempted with little evidence that the change will work.

2. Incremental change refers to a series of small change also based on low information.

3.Homeostatic –This is the most common in education. That is a small change based on more information.

4. Metamophic change – is great change supported by much information

- It is so rare that stufflebeam did include it in his CIPP model

ASSIGNMENT

How can you conduct an effective context evaluation?

-if you are a context M and E(evaluator) how can you conduct it? Refer to your decisions from psychologists, employers, learners, parents, professionals, politicians NGOs etc.

A

UHIFADHI WA REKODI ZA TARATIBU**

-Mkakati wa tatu unahusu kipengele muhimu katika maamuzi ya mradi, kama vile maudhui maalum yaliyoteuliwa, mbinu za ufundishaji zilizopangwa, au muda uliotengwa kwenye mpango kwa ajili ya shughuli fulani.

-Tathmini ya mchakato, ambayo inajumuisha mikakati hii, hufanyika katika hatua ya utekelezaji wa maendeleo ya mtaala.

-Ni hatua ya majaribio (piloting) inayofanywa ili kugundua na kurekebisha hitilafu za programu kabla ya kutekelezwa kote nchini.

TATHMINI YA MATOKEO (PRODUCT EVALUATION)

-Watathmini wa matokeo hukusanya data ili kubaini kama bidhaa ya mwisho ya mtaala inayotumika sasa inatimiza kile walichotarajia.

-Inajibu maswali kama:

→ Kwa kiwango gani malengo yaliyowekwa yanatimizwa?

-Tathmini ya matokeo huwapa watathmini taarifa zitakazowawezesha kuamua kama waendelee, wasitishe, au wabadilisha mtaala mpya.

-Inawasaidia pia kuunganisha matendo katika hatua hii ya mfano na hatua nyingine za mchakato mzima wa mabadiliko.

MFANO WA TATHMINI YA JUMLA (MACRO) WA STUFFLEBEAM

-Stufflebeam amependekeza mpango kamili wa tathmini.

-Mfano huu unatoa nafasi ya kufanya tathmini ya kimfumo kuhusu muktadha, rasilimali ingizi, mchakato na matokeo.

-Mfano unaeleza pia kuwa aina nne za maamuzi ni muhimu:

Maamuzi ya mipango – hufanyika baada ya tathmini ya muktadha.

Maamuzi ya upangaji – huanza baada ya tathmini ya rasilimali ingizi.

Maamuzi ya utekelezaji – hufuata tathmini ya mchakato.

Maamuzi ya marejeleo (recycling) – hufanywa baada ya tathmini ya matokeo.

-Stufflebeam anaeleza kuwa maamuzi hufanyika katika mazingira manne tofauti:

Mabadiliko madogo yenye taarifa nyingi.

Mabadiliko madogo yenye taarifa chache.

Mabadiliko makubwa yenye taarifa nyingi.

Mabadiliko makubwa yenye taarifa chache.

AINA ZA SHUGHULI ZA MABADILIKO

Mazinga mbalimbali ya maamuzi huzalisha aina nne za mabadiliko:

Mabadiliko ya Neomobolistiki – hutokea wakati wa kujaribu kufanya mabadiliko makubwa kwa kutumia taarifa chache. Hapa ubunifu unajaribiwa bila ushahidi wa kutosha kuwa mabadiliko yatafanikiwa.

Mabadiliko ya Kiongezeko (Incremental Change) – hutokea pale ambapo mabadiliko madogo madogo hufanywa kwa kutumia taarifa chache pia.

Mabadiliko ya Homeostasis – ndiyo ya kawaida zaidi katika elimu; ni mabadiliko madogo lakini yanategemea taarifa nyingi.

Mabadiliko ya Kimetamofosi (Metamorphic Change) – ni mabadiliko makubwa yanayoungwa mkono na taarifa nyingi.

-Ni nadra sana kutokea, hivyo Stufflebeam hakuyajumuisha kikamilifu kwenye mfano wa CIPP.

KAZI (ASSIGNMENT)

Unawezaje kufanya tathmini bora ya muktadha?

-Ikiwa wewe ni mtaalamu wa tathmini ya muktadha (context evaluator), unawezaje kuifanya?

-Rejelea maoni kutoka kwa wanasaikolojia, waajiri, wanafunzi, wazazi, wataalamu wengine, wanasiasa, mashirika yasiyo ya kiserikali (NGOs) n.k.

B

Foundations of Monitoring and Evaluation (M&E) refers to the basic principles, concepts, and structures that guide the process of tracking progress and assessing the effectiveness of programs, projects, or systems. Here’s a clear breakdown:

1. Definition

Monitoring: The continuous process of collecting, analyzing, and using information to track a program’s progress toward its objectives. It answers: Are we doing things right?

Evaluation: A systematic assessment of a program’s design, implementation, and outcomes. It answers: Are we doing the right things? and What difference are we making?

2. Key Principles

Relevance: Ensuring that the M&E activities align with the program’s goals and objectives.

Accuracy: Data collected should be correct, reliable, and credible.

Timeliness: Monitoring and evaluation should provide information at the right time for decision-making.

Participation: Stakeholders (beneficiaries, staff, and policymakers) should be involved in M&E processes.

Objectivity: Evaluations should be unbiased, focusing on evidence rather than opinions.

Transparency: Findings should be accessible and understandable to all relevant stakeholders.

3. Components of M&E

Indicators: Measurable signs of progress (e.g., literacy rate, student attendance).

Data Collection Methods: Surveys, interviews, focus groups, observation.

Data Analysis: Interpreting collected data to make sense of trends, successes, or challenges.

Reporting: Sharing results in a clear and actionable manner.

Feedback Mechanisms: Using findings to improve programs and decision-making.

4. Purpose

Improve program effectiveness and efficiency.

Enhance accountability to stakeholders.

Inform policy decisions.

Learn from successes and failures to replicate best practices.

5. Example in Education

Monitoring: Tracking school attendance daily to ensure students are attending classes.

Evaluation: Assessing whether the school feeding program improved attendance and learning outcomes after one year.